## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Rajganj | Jalpaiguri Division | CHHOTA FAPRI WATER SUPPLY SCHEME | SM/14494 | New | Material Requisition To Resource Division |  |  | RTOR000184/2023-2024 | 2047/JD | 09/01/2024 | 09/01/2024 | Resource Division | 4.67 | 0 | 0 | 0
2 | JALPAIGURI | Rajganj | Jalpaiguri Division | CHHOTA FAPRI WATER SUPPLY SCHEME | SM/14494 | New | Material Requisition To Resource Division |  |  | RTOR000002/2024-2025 | 52/JD | 09/04/2024 | 09/04/2024 | Resource Division | 12.25 | 0 | 0 | 0
3 | JALPAIGURI | Rajganj | Northern Mechanical | CHHOTA FAPRI WATER SUPPLY SCHEME | SM/14494 | New | New Service Connection Charge for CHOTA FAPTI NEPALI SCHOOL, T/W-I, under POWER HOUSE CCC, [APPLICATION NO. 4003352320, Reference ID : 403172860] |  |  | BILL/02176/2023-2024 | BP/23-24/324 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6 | 0 | 0 | 0
4 | JALPAIGURI | Rajganj | Northern Mechanical | CHHOTA FAPRI WATER SUPPLY SCHEME | SM/14494 | New | New Service Connection Charge for CHOTA FAPTI NEPALI SCHOOL, T/W-II, under POWER HOUSE CCC, [APPLICATION NO. 4003352332, Reference ID : 403172862] |  |  | BILL/02177/2023-2024 | BP/23-24/324 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.85 | 0 | 0 | 0
5 | JALPAIGURI | Rajganj | Jalpaiguri Division | CHHOTA FAPRI WATER SUPPLY SCHEME | SM/14494 | New | Construction of different components of Chotachand Fapri PWSS i.e, TW, Pump House, Water Distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block- Rajganj under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000044/2023-2024 | 221/JD | 03/05/2023 | 01/12/2025 | NARENDRA KUMAR | 196.33 | 0 | 0 | 45
6 | JALPAIGURI | Rajganj | Northern Mechanical | CHHOTA FAPRI WATER SUPPLY SCHEME | SM/14494 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHHOTA FAPRI PWSS, AT TW no I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000310/2023-2024 | 1275/NMD | 02/08/2023 | 01/09/2025 | M/S BHOWMICK & CO. | 20.44 | 0 | 0 | 70
7 | JALPAIGURI | Rajganj | Northern Mechanical | CHHOTA FAPRI WATER SUPPLY SCHEME | SM/14494 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (RAJGANJ Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000627/2024-2025 | 9/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 45.53 | 0 | 0 | 0
Total | [13 empty] | 296.07 | 0 | 0