## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | UTTAR KHUTTIMARI PIPED WATER SUPPLY SCHEME | SM/14660 | New | Construction of different components of Uttar Khuttimari PWSS i.e. TW, Pump House, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000129/2023-2024 | 405/JD | 06/06/2023 | 03/12/2023 | UNIBRO INFRASERV PRIVATE LIMITED | 280.55 | 163.06 | 58.12 | 45
2 | JALPAIGURI | Dhupguri | Northern Mechanical | UTTAR KHUTTIMARI PIPED WATER SUPPLY SCHEME | SM/14660 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for UTTAR KHUTTIMARI PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD,Driller-in-Charge | Junior Engineer | ORD/000022/2023-2024 | 464/NMD | 25/04/2023 | 01/07/2025 | MALAY KUMAR SAHA | 22.13 | 15.22 | 68.81 | 100
3 | JALPAIGURI | Dhupguri | Jalpaiguri Division | UTTAR KHUTTIMARI PIPED WATER SUPPLY SCHEME | SM/14660 | New | Material Requisition To Resource Division |  |  | RTOR000020/2023-2024 | 164/JD | 28/04/2023 | 28/04/2023 | Resource Division | 13.57 | 0 | 0 | 0
4 | JALPAIGURI | Dhupguri | Jalpaiguri Division | UTTAR KHUTTIMARI PIPED WATER SUPPLY SCHEME | SM/14660 | New | Material Requisition To Resource Division |  |  | RTOR000132/2023-2024 | 1881/JD | 20/12/2023 | 20/12/2023 | Resource Division | 6.62 | 0 | 0 | 0
5 | JALPAIGURI | Dhupguri | Jalpaiguri Division | UTTAR KHUTTIMARI PIPED WATER SUPPLY SCHEME | SM/14660 | New | Supply and Delivery at site of UPVC pipe of 250mm dia for tube well of Uttar Khuttimari PWSS under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ |  | ORD/000736/2023-2024 | 2456/JD | 23/02/2024 | 01/03/2024 | UNIBRO INFRASERV PRIVATE LIMITED | 2.46 | 0 | 0 | 0
6 | JALPAIGURI | Dhupguri | Northern Mechanical | UTTAR KHUTTIMARI PIPED WATER SUPPLY SCHEME | SM/14660 | New | New Service Connection Charge for UTTAR KHUTTIMARI, T/W-I, under GAIRKATA CCC, [APPLICATION NO. 100000101600, Reference ID : 860292660] |  |  | BILL/02171/2023-2024 | BP/23-24/324 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3 | 0 | 0 | 0
7 | JALPAIGURI | Dhupguri | Northern Mechanical | UTTAR KHUTTIMARI PIPED WATER SUPPLY SCHEME | SM/14660 | New | New Service Connection Charge for UTTAR KHUTTIMARI, T/W-II, under GAIRKATA CCC, [APPLICATION NO. 100000101602, Reference ID : 860292662] |  |  | BILL/02169/2023-2024 | BP/23-24/324 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.42 | 0 | 0 | 0
8 | JALPAIGURI | Dhupguri | Northern Mechanical | UTTAR KHUTTIMARI PIPED WATER SUPPLY SCHEME | SM/14660 | New | New Service Connection Charge for UTTAR KHUTTIMARI, T/W-I, under GAIRKATA CCC, [APPLICATION NO. 4003356966, Reference ID : 403176985] |  |  | BILL/02170/2023-2024 | BP/23-24/324 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.71 | 0 | 0 | 0
9 | JALPAIGURI | Dhupguri | Northern Mechanical | UTTAR KHUTTIMARI PIPED WATER SUPPLY SCHEME | SM/14660 | New | New Service Connection Charge for UTTAR KHUTTIMARI, T/W-II, under GAIRKATA CCC, [APPLICATION NO. 4003356873, Reference ID : 403176987] |  |  | BILL/02168/2023-2024 | BP/23-24/324 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.71 | 0 | 0 | 0
10 | JALPAIGURI | Dhupguri | Jalpaiguri Division | UTTAR KHUTTIMARI PIPED WATER SUPPLY SCHEME | SM/14660 | New | Providing Balance Functional Household Tap Connection (FHTC) in the command area of Uttar Kuttimari PWSS in connection with Jal Jeevan Mission at Block Dhupguri under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000605/2024-2025 | 485/JD | 11/03/2025 | 05/04/2025 | KABYA ENTERPRISE | 12.58 | 0 | 0 | 0
11 | JALPAIGURI | Dhupguri | Jalpaiguri Division | UTTAR KHUTTIMARI PIPED WATER SUPPLY SCHEME | SM/14660 | New | Material Requisition To Resource Division |  |  | RTOR000093/2024-2025 | 286/JD | 10/02/2025 | 10/02/2025 | Resource Division | 75.27 | 0 | 0 | 0
Total | [13 empty] | 423.02 | 178.29 | 42.15