## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/14664 | New | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 147/JD | 28/04/2023 |  | Resource Division | 32.33 | 0 | 0 | 0
2 | JALPAIGURI | Dhupguri | Northern Mechanical | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/14664 | New | New Service Connection Charge for GAIRKATA, T/W III, under DHUPGURI CCC, [APPLICATION NO. 4003214185, Reference ID : 403062249] |  |  | BILL/01068/2023-2024 | BP/23-24/106 | 30/09/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.66 | 0 | 0 | 0
3 | JALPAIGURI | Dhupguri | Northern Mechanical | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/14664 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augmentation of GAIRKATA PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000874/2022-2023 | 338/NMD | 29/03/2023 | 28/04/2023 | M/S ROYAL ENTERPRISE | 10.24 | 7.78 | 75.94 | 60
4 | JALPAIGURI | Dhupguri | Jalpaiguri Division | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/14664 | New | Material Requisition To Resource Division |  |  | RTOR000117/2023-2024 | 1828/JD | 15/12/2023 |  | Resource Division | 14.29 | 0 | 0 | 0
5 | JALPAIGURI | Dhupguri | Northern Mechanical | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/14664 | New | Additional works in connection with supply, installation and commissioning and trial operation of electromechanical accessories of W/S system at GAIRKATA W/S scheme for T.W No. -I, II & III in the dist. of Jalpaiguri. | Driller-in-Charge | Junior Engineer | ORD/001041/2023-2024 | 01/DSD | 04/01/2024 | 11/01/2024 | SARKAR ELECTRIC | 0.93 | 0.46 | 49.71 | 100
6 | JALPAIGURI | Dhupguri | Jalpaiguri Division | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/14664 | New | Construction of different components of Gairkhata Tea Garden (D) PWSS i.e. T.W. Pump House, Water Distribution Network, OHR, Rising Main,FHTC etc. In connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000440/2022-2023 | 677/JD | 16/03/2023 | 12/09/2023 | SUKES BASU MAJUMDAR | 448.24 | 375.56 | 83.78 | 100
7 | JALPAIGURI | Dhupguri | Northern Mechanical | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/14664 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for GAIRKHATA TEA GARDEN (D) PWSS, at TW NO I,II,III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000140/2023-2024 | 1194/NMD | 21/07/2023 | 20/08/2023 | SARKAR ELECTRIC | 40.62 | 37.05 | 91.22 | 100
8 | JALPAIGURI | Dhupguri | Jalpaiguri Division | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/14664 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
9 | JALPAIGURI | Dhupguri | Jalpaiguri Division | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/14664 | New | Construction of Boundary Wall, Rising Main & Providing FHTC at Rejuvenation of Sajnapara PWSS in connection with Jal Jeevan Mission at Banarhat Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000535/2023-2024 | 1976/JD | 03/01/2024 | 02/02/2024 | ALOKE DEY | 44.98 | 0 | 0 | 10
Total | [13 empty] | 626.94 | 420.85 | 67.13