## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/14664 | New | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 147/JD | 28/04/2023 | 28/04/2023 | Resource Division | 32.33 | 0 | 0 | 0
2 | JALPAIGURI | Dhupguri | Jalpaiguri Division | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/14664 | New | Material Requisition To Resource Division |  |  | RTOR000117/2023-2024 | 1828/JD | 15/12/2023 | 15/12/2023 | Resource Division | 14.29 | 0 | 0 | 0
3 | JALPAIGURI | Dhupguri | Northern Mechanical | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/14664 | New | New Service Connection Charge for GAIRKATA, T/W III, under DHUPGURI CCC, [APPLICATION NO. 4003214185, Reference ID : 403062249] |  |  | BILL/01068/2023-2024 | BP/23-24/106 | 30/09/2023 | 30/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.66 | 0 | 0 | 0
4 | JALPAIGURI | Dhupguri | Jalpaiguri Division | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/14664 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
5 | JALPAIGURI | Dhupguri | Jalpaiguri Division | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/14664 | New | Construction of different components of Gairkhata Tea Garden (D) PWSS i.e. T.W. Pump House, Water Distribution Network, OHR, Rising Main,FHTC etc. In connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000440/2022-2023 | 677/JD | 16/03/2023 | 13/06/2024 | SUKES BASU MAJUMDAR | 448.24 | 0 | 0 | 100
6 | JALPAIGURI | Dhupguri | Northern Mechanical | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/14664 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for GAIRKHATA TEA GARDEN (D) PWSS, at TW NO I,II,III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000140/2023-2024 | 1194/NMD | 21/07/2023 | 20/08/2023 | SARKAR ELECTRIC | 40.62 | 0 | 0 | 100
7 | JALPAIGURI | Dhupguri | Northern Mechanical | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/14664 | New | Additional works in connection with supply, installation and commissioning and trial operation of electromechanical accessories of W/S system at GAIRKATA W/S scheme for T.W No. -I, II & III in the dist. of Jalpaiguri. | Driller-in-Charge | Junior Engineer | ORD/001041/2023-2024 | 01/DSD | 04/01/2024 | 11/01/2024 | SARKAR ELECTRIC | 0.93 | 0 | 0 | 100
8 | JALPAIGURI | Dhupguri | Northern Mechanical | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/14664 | New | Fuel, Lubricant Charges for Government Inspection Vechile under NMD PHE Dte Invoice No : 0007(A)/2024-2025 , Dt - 31/10/2024 Vechile no - WB73B/7824 for the month of october 2024 |  |  | BILL/01680/2024-2025 |  | 06/12/2024 | 06/12/2024 | M/S MILLENNIUM FUEL CENTRE | 0.1 | 0 | 0 | 0
9 | JALPAIGURI | Dhupguri | Northern Mechanical | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/14664 | New | Fuel Charges for Government Inspection Vechile under NMD PHE Dte Invoice No : 0006/2024-2025 , Dt - 30/09/2024 Vechile no - WGX4997 for the month of september 2024 |  |  | BILL/01681/2024-2025 |  | 06/12/2024 | 06/12/2024 | M/S MILLENNIUM FUEL CENTRE | 0.2 | 0 | 0 | 0
10 | JALPAIGURI | Dhupguri | Northern Mechanical | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/14664 | New | Fuel Charges for Government Inspection Vechile under NMD PHE Dte Invoice No : 0007/2024-2025 , Dt - 31/10/2024 Vechile no - WGX4997 for the month of OCtober 2024 |  |  | BILL/01679/2024-2025 |  | 06/12/2024 | 06/12/2024 | M/S MILLENNIUM FUEL CENTRE | 0.09 | 0 | 0 | 0
11 | JALPAIGURI | Dhupguri | Jalpaiguri Division | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/14664 | New | Construction of Boundary Wall, Rising Main, Laying Distribution System at 3rd Tube Well Site and Providing Functional Household Tap Connection of Sajnapara around Gairkata Tea Garden Piped Water Supply Scheme in connection with Jal Jeevan Mission at Banarhat Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000680/2024-2025 | 459/JD | 11/03/2025 | 01/08/2025 | ALOKE DEY | 56.41 | 0 | 0 | 20
12 | JALPAIGURI | Dhupguri | Northern Mechanical | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/14664 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augmentation of GAIRKATA PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD,Driller-in-Charge | Junior Engineer | ORD/000874/2022-2023 | 338/NMD | 29/03/2023 | 01/06/2025 | M/S ROYAL ENTERPRISE | 10.24 | 0 | 0 | 100
Total | [13 empty] | 638.76 | 0 | 0