## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/14665 | New | Material Requisition To Resource Division |  |  | RTOR000008/2023-2024 | 152/JD | 28/04/2023 | 28/04/2023 | Resource Division | 26.83 | 0 | 0 | 0
2 | JALPAIGURI | Dhupguri | Jalpaiguri Division | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/14665 | New | Material Requisition To Resource Division |  |  | RTOR000124/2023-2024 | 1838/JD | 15/12/2023 | 15/12/2023 | Resource Division | 2.62 | 0 | 0 | 0
3 | JALPAIGURI | Dhupguri | Jalpaiguri Division | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/14665 | New | Construction of different components of Gadang Pratham Khanda PWSS i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc. In connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000475/2022-2023 | 779/JD | 27/03/2023 | 23/09/2023 | M/S. DOLPHIN CONSTRUCTION CO. | 222.91 | 127.77 | 57.32 | 20
4 | JALPAIGURI | Dhupguri | Northern Mechanical | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/14665 | New | New Service Connection Charge for GADANG PRATHAM KHANDA PWSS , T/W-I under DHUPGURI CCC, APPLICATION NO. 4003412908 Reference ID : 403221510 |  |  | BILL/00388/2024-2025 | BP/24-25/73 | 30/05/2024 | 30/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.3 | 0 | 0 | 0
5 | JALPAIGURI | Dhupguri | Northern Mechanical | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/14665 | New | New Service Connection Charge for GADANG PRATHAM KHANDA PWSS, TW no II, under DHUPGURI CCC APPLICATION NO. 4003290916 Consumer ID : 403123851 |  |  | BILL/00536/2024-2025 | BP/24-25/130 | 24/07/2024 | 24/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.42 | 0 | 0 | 0
6 | JALPAIGURI | Dhupguri | Northern Mechanical | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/14665 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
7 | JALPAIGURI | Dhupguri | Northern Mechanical | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/14665 | New | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Driller-in-Charge |  | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 25/03/2025 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
8 | JALPAIGURI | Dhupguri | Northern Mechanical | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/14665 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/001049/2024-2025 | 31/NMD | 06/01/2025 | 05/02/2025 | ANIMA ENTERPRISE | 15.32 | 0 | 0 | 0
Total | [13 empty] | 370.17 | 127.77 | 34.52