## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Northern Mechanical | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for GENDRAPARA TG (D) PWSS, TW NO I, II AND III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000240/2023-2024 | 1254/NMD | 31/07/2023 | 01/10/2024 | SUNRISE ENGINEERING CORPORATION | 36.78 | 34.56 | 93.97 | 100
2 | JALPAIGURI | Dhupguri | Jalpaiguri Division | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | New | Construction of different components of Gendrapara Tea Graden PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block Banerhat under Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | ORD/000447/2022-2023 | 717/JD | 20/03/2023 | 16/08/2025 | ANUGRAH CONSTRUCTION PVT. LTD. | 424.78 | 343.97 | 80.98 | 60
3 | JALPAIGURI | Dhupguri | Jalpaiguri Division | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | New | Material Requisition To Resource Division |  |  | RTOR000060/2023-2024 | 1093/JD | 24/08/2023 | 24/08/2023 | Resource Division | 27.95 | 0 | 0 | 0
4 | JALPAIGURI | Dhupguri | Jalpaiguri Division | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | New | Material Requisition To Resource Division |  |  | RTOR000118/2023-2024 | 1829/JD | 15/12/2023 | 15/12/2023 | Resource Division | 14.72 | 0 | 0 | 0
5 | JALPAIGURI | Dhupguri | Northern Mechanical | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | New | New Service Connection Charge for GENDRAPARA TEA GAEDEN, T/W II under BANARHAT CCC [APPLICATION NO. 4003193576 ; Reference ID : 403045947] |  |  | BILL/01003/2023-2024 | BP/23-24/98 | 12/09/2023 | 12/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
6 | JALPAIGURI | Dhupguri | Northern Mechanical | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | New | Infrastructure Cost for GENDRAPARA TEA GAEDEN, T/W III under BANARHAT CCC [APPLICATION NO. 100000083811 ; Reference ID : 860275311] |  |  | BILL/01006/2023-2024 | BP/23-24/98 | 12/09/2023 | 12/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.38 | 0 | 0 | 0
7 | JALPAIGURI | Dhupguri | Northern Mechanical | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | New | Infrastructure Cost for GENDRAPARA TEA GAEDEN, T/W I under BANARHAT CCC [APPLICATION NO. 100000083816 ; Reference ID : 860275316] |  |  | BILL/01002/2023-2024 | BP/23-24/98 | 12/09/2023 | 12/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.68 | 0 | 0 | 0
8 | JALPAIGURI | Dhupguri | Northern Mechanical | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | New | Infrastructure Cost for GENDRAPARA TEA GAEDEN, T/W II under BANARHAT CCC [APPLICATION NO. 100000083810 ; Reference ID : 860275310] |  |  | BILL/01004/2023-2024 | BP/23-24/98 | 12/09/2023 | 12/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.03 | 0 | 0 | 0
9 | JALPAIGURI | Dhupguri | Northern Mechanical | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | New | New Service Connection Charge for GENDRAPARA TEA GAEDEN, T/W III under BANARHAT CCC [APPLICATION NO. 4003193581 ; Reference ID : 403045948] |  |  | BILL/01005/2023-2024 | BP/23-24/98 | 12/09/2023 | 12/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
10 | JALPAIGURI | Dhupguri | Northern Mechanical | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | New | New Service Connection Charge for GENDRAPARA TEA GAEDEN, T/W I under BANARHAT CCC [APPLICATION NO. 4003193569 ; Reference ID : 403045945] |  |  | BILL/01001/2023-2024 | BP/23-24/98 | 12/09/2023 | 12/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
11 | JALPAIGURI | Dhupguri | Jalpaiguri Division | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
12 | JALPAIGURI | Dhupguri | Jalpaiguri Division | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | New | Balance Laying Distribution System and Functional Household Tap Connection in connection with Jal Jeevan Mission for Gendrapara Tea Garden Piped Water Supply Scheme Block - Banarhat under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000528/2024-2025 | 125/JD | 16/01/2025 | 07/03/2025 | SANJIT SAHA | 56.46 | 0 | 0 | 0
13 | JALPAIGURI | Dhupguri | Northern Mechanical | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: BANARHAT, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/001045/2024-2025 | 30/NMD | 06/01/2025 | 05/02/2025 | GEETA CONSTRUCTION | 12.33 | 0 | 0 | 0
14 | JALPAIGURI | Dhupguri | Northern Mechanical | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (BANARHAT Block ) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000987/2024-2025 | 11/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 57.53 | 0 | 0 | 0
15 | JALPAIGURI | Dhupguri | Northern Mechanical | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | New | Installation of two tank chlorination system at different water supply scheme UNDER JJM under BANARHAT Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Driller-in-Charge |  | ORD/001136/2024-2025 | 52/DSD | 10/03/2025 | 25/03/2025 | D.K. & SONS | 1.39 | 0 | 0 | 0
16 | JALPAIGURI | Dhupguri | Jalpaiguri Division | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | New | Material Requisition To Resource Division |  |  | RTOR000006/2025-2026 | 908/JD | 10/05/2025 | 10/05/2025 | Resource Division | 21.56 | 0 | 0 | 0
Total | [13 empty] | 694.29 | 378.54 | 54.52