## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Maynaguri | Jalpaiguri Division | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME | SM/14667 | New | Material Requisition To Resource Division |  |  | RTOR000022/2023-2024 | 166/JD | 28/04/2023 | 28/04/2023 | Resource Division | 15.92 | 0 | 0 | 0
2 | JALPAIGURI | Maynaguri | Jalpaiguri Division | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME | SM/14667 | New | Construction of different components of Paschim Baragila PWSS i.e. TW, pump Houses, Water distribution network, OHR, RISING MAIN, FHTC etc. under Jal Jeeban Mission at Block - Maynaguri under Jalpaiguri Divission, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000470/2022-2023 | 776/JD | 27/03/2023 | 23/09/2023 | TIRTHANKAR CHOWDHURY | 234.57 | 159.05 | 67.81 | 75
3 | JALPAIGURI | Maynaguri | Northern Mechanical | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME | SM/14667 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PASCHIM BARAGILA PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000844/2022-2023 | 272/NMD | 21/03/2023 | 20/04/2023 | S.P. ENTERPRISE | 20.63 | 16.5 | 79.98 | 80
4 | JALPAIGURI | Maynaguri | Jalpaiguri Division | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME | SM/14667 | New | Construction of Boundary Wall at H/W site including rising main and interconnections of PASCHIM BARAGILA PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000779/2023-2024 | 2496/JD | 28/02/2024 | 13/04/2024 | TIRTHANKAR CHOWDHURY | 16.53 | 0 | 0 | 0
5 | JALPAIGURI | Maynaguri | Jalpaiguri Division | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME | SM/14667 | New | Balance Laying Distribution System and Providing Functional House Hold Tap Connection at Paschimbaragila PWSS in Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000455/2024-2025 | 2334./JD | 12/12/2024 | 26/01/2025 | PRITAM DUTTA | 21.76 | 0 | 0 | 0
6 | JALPAIGURI | Maynaguri | Jalpaiguri Division | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME | SM/14667 | New | Material Requisition To Resource Division |  |  | RTOR000187/2023-2024 | 2050/JD | 09/01/2024 | 09/01/2024 | Resource Division | 2.89 | 0 | 0 | 0
7 | JALPAIGURI | Maynaguri | Northern Mechanical | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME | SM/14667 | New | New Service Connection Charge for PASCHIM BOROGILA, T/W No. I, under MAYNAGURI CCC, [APPLICATION NO. 4003266412, Reference ID : 403105853] |  |  | BILL/01285/2023-2024 | 23-24/156&164 | 12/12/2023 | 12/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.99 | 0 | 0 | 0
8 | JALPAIGURI | Maynaguri | Jalpaiguri Division | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME | SM/14667 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  |  | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 03/04/2024 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
9 | JALPAIGURI | Maynaguri | Northern Mechanical | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME | SM/14667 | New | New Service Connection Charge for PASCHIM BOROGILA, T/W No. II, under MAYNAGURI CCC, [APPLICATION NO. 4003266398, Reference ID : 403105500] |  |  | BILL/01284/2023-2024 | 23-24/156&164 | 12/12/2023 | 12/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.18 | 0 | 0 | 0
10 | JALPAIGURI | Maynaguri | Jalpaiguri Division | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME | SM/14667 | New | Construction of Boundary Wall at 2nd Pump House site including raising main and interconnection of PASCHIM BARAGILA PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000672/2023-2024 | 167/RWS | 15/02/2024 | 07/02/2025 | EDIFICE ENTERPRISE | 7.52 | 0 | 0 | 100
11 | JALPAIGURI | Maynaguri | Jalpaiguri Division | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME | SM/14667 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Maynaguri Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000061/2024-2025 | 944/JD | 07/08/2024 | 22/08/2024 | GURUKUL INFOTECH | 4.43 | 0 | 0 | 100
12 | JALPAIGURI | Maynaguri | Northern Mechanical | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME | SM/14667 | New | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000776/2024-2025 | 290/HQ/NMD | 24/01/2025 | 23/02/2025 | S.P. ENTERPRISE | 2 | 0 | 0 | 0
13 | JALPAIGURI | Maynaguri | Northern Mechanical | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME | SM/14667 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAYNAGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001007/2024-2025 | 27/NMD | 06/01/2025 | 05/02/2025 | M/S BHOWMICK & CO. | 18.4 | 0 | 0 | 0
14 | JALPAIGURI | Maynaguri | Northern Mechanical | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME | SM/14667 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000002/2025-2026 | 961/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0 | 0
15 | JALPAIGURI | Maynaguri | Northern Mechanical | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME | SM/14667 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
Total | [13 empty] | 846.42 | 175.55 | 20.74