## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | Material Requisition To Resource Division |  |  | RTOR000064/2023-2024 | 1092/JD | 24/08/2023 | 24/08/2023 | Resource Division | 60.02 | 0 | 0 | 0
2 | JALPAIGURI | Mal | Jalpaiguri Division | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | Material Requisition To Resource Division |  |  | RTOR000154/2023-2024 | 2012/JD | 09/01/2024 | 09/01/2024 | Resource Division | 15.28 | 0 | 0 | 0
3 | JALPAIGURI | Mal | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | New Service Connection Charge for KANTADIGHI KUMARPARA TG PWSS, T/W No. I, under MAL CCC [APPLICATION NO. 4003303019 , Reference ID : 403132354] |  |  | BILL/01791/2023-2024 | BP/23-24/261 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
4 | JALPAIGURI | Mal | Jalpaiguri Division | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  |  | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 07/03/2024 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
5 | JALPAIGURI | Mal | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | New Service Connection Charge for KANTADIGHI KUMARPARA TG PWSS, T/W No. II, under MAL CCC [APPLICATION NO. 4003303022 , Reference ID : 403132353] |  |  | BILL/01793/2023-2024 | BP/23-24/262 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
6 | JALPAIGURI | Mal | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | Infrastructure Cost for KANTADIGHI KUMARPARA TG PWSS, T/W No. II, under MAL CCC [APPLICATION NO. 100000096844 , Reference ID : 860287694] |  |  | BILL/01794/2023-2024 | BP/23-24/263 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.18 | 0 | 0 | 0
7 | JALPAIGURI | Mal | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | New Service Connection Charge for KANTADIGHI KUMARPARA TG PWSS, T/W No. III, under MAL CCC [APPLICATION NO. 4003303010 , Reference ID : 403132351] |  |  | BILL/01795/2023-2024 | BP/23-24/264 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
8 | JALPAIGURI | Mal | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | Infrastructure Cost for KANTADIGHI KUMARPARA TG PWSS, T/W No. III, under MAL CCC [APPLICATION NO. 100000096846 , Reference ID : 860287696] |  |  | BILL/01796/2023-2024 | BP/23-24/265 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.25 | 0 | 0 | 0
9 | JALPAIGURI | Mal | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | Infrastructure Cost for KANTADIGHI KUMARPARA TG PWSS, T/W No. I, under MAL CCC [APPLICATION NO. 100000096843 , Reference ID : 860287693] |  |  | BILL/01792/2023-2024 | BP/23-24/260 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.14 | 0 | 0 | 0
10 | JALPAIGURI | Mal | Jalpaiguri Division | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | Balance works Distribtion System and Functional Household Tap Connection (FHTC) including Different Components of Kantadighi Kumar Para TG PWSS i.e. TW, Pump House, Boundary Wall, Rising Main etc. in connection with Jal Jeevan Mission at Block-Mal under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000456/2024-2025 | 2037/JD | 21/11/2024 | 01/04/2026 | SAPTASWA SARKAR | 82.16 | 0 | 0 | 40
11 | JALPAIGURI | Mal | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAL, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001005/2024-2025 | 25/NMD | 06/01/2025 | 05/02/2025 | CHOWDHURY AND BASU ENTERPRISE | 15.33 | 0 | 0 | 0
12 | JALPAIGURI | Mal | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
13 | JALPAIGURI | Mal | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
14 | JALPAIGURI | Mal | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KANTADIGHI KUMAPARA TG PWSS at TW NO III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001571/2023-2024 | 655/NMD | 15/03/2024 | 01/11/2024 | BONANZA ENTERPRISE | 12.34 | 11.73 | 95.08 | 100
15 | JALPAIGURI | Mal | Jalpaiguri Division | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000060/2024-2025 | 943/JD | 07/08/2024 | 11/12/2025 | GURUKUL INFOTECH | 4.83 | 0 | 0 | 100
Total | [13 empty] | 725.36 | 11.73 | 1.62