## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14880 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
2 | JALPAIGURI | Mal | Jalpaiguri Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14880 | New | Balance work of Distribution Network and Functional Household Tap Connection (FHTC) of Rangamati Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000432/2024-2025 | 2273/JD | 05/12/2024 | 03/02/2025 | LAKSHMI IRON | 26.64 | 0 | 0 | 0
3 | JALPAIGURI | Mal | Jalpaiguri Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14880 | New | Material Requisition To Resource Division |  |  | RTOR000151/2023-2024 | 2019/JD | 09/01/2024 | 09/01/2024 | Resource Division | 12.63 | 0 | 0 | 0
4 | JALPAIGURI | Mal | Northern Mechanical | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14880 | New | Infrastructure Cost for RANGAMATI TEA GARDEN, T/W No. I, under MAL CCC [APPLICATION NO. 100000098979 , Reference ID : 860290249] |  |  | BILL/01993/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.3 | 0 | 0 | 0
5 | JALPAIGURI | Mal | Northern Mechanical | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14880 | New | Infrastructure Cost for RANGAMATI TEA GARDEN, T/W No.II, under MAL CCC [APPLICATION NO. 100000099050 , Reference ID : 860290250] |  |  | BILL/01991/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.28 | 0 | 0 | 0
6 | JALPAIGURI | Mal | Northern Mechanical | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14880 | New | New Service Connection Charge for RANGAMATI TEA GARDEN, T/W No. I, under MAL CCC [APPLICATION NO. 4003325220 , Reference ID : 403151422] |  |  | BILL/01992/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.83 | 0 | 0 | 0
7 | JALPAIGURI | Mal | Northern Mechanical | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14880 | New | New Service Connection Charge for RANGAMATI TEA GARDEN, T/W No. II, under MAL CCC [APPLICATION NO. 4003325230 , Reference ID : 403151421] |  |  | BILL/01990/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.83 | 0 | 0 | 0
8 | JALPAIGURI | Mal | Northern Mechanical | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14880 | New | Infrastructure development cost for new service connection at RANGAMATI TG,T/W-III, OODLABARI CCC APPLICATION NO. 100000110603 Reference ID : 860303203 |  |  | BILL/00489/2024-2025 | BP/24-25/101 | 25/06/2024 | 25/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.49 | 0 | 0 | 0
9 | JALPAIGURI | Mal | Jalpaiguri Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14880 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  |  | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 07/03/2024 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
10 | JALPAIGURI | Mal | Northern Mechanical | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14880 | New | New Service Connection Charge for RANGAMATI TG,T/W-III, OODLABARI CCC APPLICATION NO. 4003437136 Reference ID : 403237579 |  |  | BILL/00490/2024-2025 | BP/24-25/101 | 25/06/2024 | 25/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
11 | JALPAIGURI | Mal | Jalpaiguri Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14880 | New | Construction of different components of Rangamati Tea Garden PWSS i.e. TW, Pump Houses, IEP, Blower Room, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 940/JD | 08/08/2023 | 26/07/2025 | M/S SARKAR ENTERPRISE | 360.92 | 70.39 | 19.5 | 22
12 | JALPAIGURI | Mal | Northern Mechanical | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14880 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for RANGAMATI TG PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000671/2023-2024 | 1486/NMD | 17/08/2023 | 01/02/2026 | M/S UTPAL CHAKRABORTY & CO. | 36.59 | 0 | 0 | 50
13 | JALPAIGURI | Mal | Jalpaiguri Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14880 | New | Balance work of Distribution System and Functional Household Tap Connection (FHTC) including different components of Rangamati Tea Garden PWSS i.e. Tube Well, Pump House, Boundary Wall, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000012/2025-2026 | 894/JD | 08/05/2025 | 06/08/2025 | UMA CONSTRUCTION | 41.93 | 0 | 0 | 0
Total | [13 empty] | 568.1 | 70.39 | 12.39