## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME | SM/14881 | New | Material Requisition To Resource Division |  |  | RTOR000108/2023-2024 | 1368/JD | 27/09/2023 | 27/09/2023 | Resource Division | 22.35 | 0 | 0 | 0
2 | JALPAIGURI | Mal | Jalpaiguri Division | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME | SM/14881 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
3 | JALPAIGURI | Mal | Jalpaiguri Division | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME | SM/14881 | New | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Kranti block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. | Assistant Engineer | Junior Engineer | ORD/000475/2023-2024 | 1294/RWS | 29/11/2023 | 29/12/2023 | SUKES BASU MAJUMDAR | 2.34 | 0 | 0 | 100
4 | JALPAIGURI | Mal | Jalpaiguri Division | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME | SM/14881 | New | Material Requisition To Resource Division |  |  | RTOR000149/2023-2024 | 2018/JD | 09/01/2024 | 09/01/2024 | Resource Division | 12.97 | 0 | 0 | 0
5 | JALPAIGURI | Mal | Northern Mechanical | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME | SM/14881 | New | New Service Connection Charge for Purba Dalaigaon, TW NO-I, KRANTI CCC APPLICATION NO. 4003373951 Reference ID : 403190123 |  |  | BILL/00212/2024-2025 | BP/24-25/25 | 09/05/2024 | 09/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
6 | JALPAIGURI | Mal | Northern Mechanical | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME | SM/14881 | New | Infrastructure development cost for new service connection at Purba Dalaigaon, TW NO-I, KRANTI CCC APPLICATION NO. 100000103006 Reference ID : 860295356 |  |  | BILL/00213/2024-2025 | BP/24-25/25 | 09/05/2024 | 09/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6 | 0 | 0 | 0
7 | JALPAIGURI | Mal | Northern Mechanical | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME | SM/14881 | New | New Service Connection Charge for PURBA DOLAIGAON,TW NO-II, KRANTI CCC APPLICATION NO. 4003373939 Reference ID : 403190122 |  |  | BILL/00514/2024-2025 | BP/24-25/123 | 16/07/2024 | 16/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
8 | JALPAIGURI | Mal | Northern Mechanical | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME | SM/14881 | New | Infrastructure development cost for new service connection at PURBA DOLAIGAON,TW NO-II, KRANTI CCC APPLICATION NO. 100000112283 Reference ID : 860304193 |  |  | BILL/00515/2024-2025 | BP/24-25/123 | 16/07/2024 | 16/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.89 | 0 | 0 | 0
9 | JALPAIGURI | Mal | Jalpaiguri Division | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME | SM/14881 | New | Construction of different components of Purba Dolaigaon PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block-Kranti under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000070/2023-2024 | 355/JD | 24/05/2023 | 01/10/2025 | BHUWALKA DEVELOPMENTS PRIVATE LIMITED | 423.12 | 0 | 0 | 50
10 | JALPAIGURI | Mal | Jalpaiguri Division | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME | SM/14881 | New | Balance Laying Distribution Network including Construction of Additional Components of Purba Dolaigaon PWSS i.e. TW, Pump House, Boundary Wall, Rising main etc. in connection with Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000677/2024-2025 | 487/JD | 11/03/2025 | 10/05/2025 | DEBASISH DEY | 47.56 | 0 | 0 | 0
11 | JALPAIGURI | Mal | Northern Mechanical | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME | SM/14881 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KRANTI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001008/2024-2025 | 28/NMD | 06/01/2025 | 05/02/2025 | M/S PARITOSH BHOWMICK AND CO. | 12.16 | 0 | 0 | 0
12 | JALPAIGURI | Mal | Northern Mechanical | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME | SM/14881 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector at PURBA DOLAIGAON PWSS for T/W No. I and II in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000847/2024-2025 | 586/NMD | 07/02/2025 | 01/07/2025 | S.P. ENTERPRISE | 23.88 | 0 | 0 | 80
13 | JALPAIGURI | Mal | Jalpaiguri Division | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME | SM/14881 | New | Construction of Boundary Wall, Land development, pathway, surface drain etc. i.c.w. Purba Dolaigaon PWSS 2nd TW Site under Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000101/2025-2026 | 480/RWS | 29/05/2025 | 28/06/2025 | ADITRI ENTERPRISE | 8.36 | 0 | 0 | 0
14 | JALPAIGURI | Mal | Northern Mechanical | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME | SM/14881 | New | Installation of two tank chlorination system at different water supply scheme of JJM under Kranti Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001412/2024-2025 | 56/HQ/NMD | 06/01/2025 | 13/01/2025 | SUMON ELECTRICAL | 0.31 | 0 | 0 | 0
Total | [13 empty] | 598.96 | 0 | 0