## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/14883 | New | Sinking of 2 Nos. Big Dia Tube Well by Modified DTH - ODEX Method at Tunbari Tea Gargen Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000469/2023-2024 | 1762/JD | 08/12/2023 | 07/01/2024 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 33.23 | 0 | 0 | 100
2 | JALPAIGURI | Mal | Jalpaiguri Division | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/14883 | New | Material Requisition To Resource Division |  |  | RTOR000062/2023-2024 | 1091/JD | 24/08/2023 | 24/08/2023 | Resource Division | 35.62 | 0 | 0 | 0
3 | JALPAIGURI | Mal | Jalpaiguri Division | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/14883 | New | Material Requisition To Resource Division |  |  | RTOR000142/2023-2024 | 1888/JD | 20/12/2023 | 20/12/2023 | Resource Division | 9.92 | 0 | 0 | 0
4 | JALPAIGURI | Mal | Jalpaiguri Division | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/14883 | New | Construction of different components of Tunbari Tea Garden (P) PWSS i.e. TW, Pump Houses, IEP, Blower Room, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block ¿ Mal under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000060/2023-2024 | 265/JD | 10/05/2023 | 06/11/2023 | M/S SARKAR ENTERPRISE | 304.78 | 0 | 0 | 70
5 | JALPAIGURI | Mal | Northern Mechanical | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/14883 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for TUNBARI TG PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000449/2023-2024 | 1388/NMD | 09/08/2023 | 08/09/2023 | M/S CHANDRANATH MUKHERJEE | 25.75 | 0 | 0 | 80
6 | JALPAIGURI | Mal | Jalpaiguri Division | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/14883 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
7 | JALPAIGURI | Mal | Jalpaiguri Division | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/14883 | New | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Malbazar block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. | Assistant Engineer | Junior Engineer | ORD/000463/2023-2024 | 1291/RWS | 29/11/2023 | 29/12/2023 | B.M CONSTRUCTION | 3.89 | 0 | 0 | 100
8 | JALPAIGURI | Mal | Northern Mechanical | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/14883 | New | Infrastructure development cost for new service connection at TUNBARI TG, TW NO-I, MAL CCC APPLICATION NO. 100000102137 Reference ID : 860293897 |  |  | BILL/00194/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.85 | 0 | 0 | 0
9 | JALPAIGURI | Mal | Northern Mechanical | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/14883 | New | New Service Connection Charge for TUNBARI TG, TW NO-I, MAL CCC APPLICATION NO. 4003299893 Reference ID : 403130044 |  |  | BILL/00193/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
10 | JALPAIGURI | Mal | Northern Mechanical | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/14883 | New | New Service Connection Charge for TUNBARI TG, TW NO-II, MAL CCC APPLICATION NO. 4003299902 Reference ID : 403130042 |  |  | BILL/00195/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
11 | JALPAIGURI | Mal | Northern Mechanical | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/14883 | New | Infrastructure development cost for new service connection at TUNBARI TG, TW NO-II, MAL CCC APPLICATION NO. 100000102138 Reference ID : 860293898 |  |  | BILL/00196/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.32 | 0 | 0 | 0
12 | JALPAIGURI | Mal | Jalpaiguri Division | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/14883 | New | Laying distribution system with other allied works in connection with Jal Jeevan Mission at Tunbari Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  |  | ORD/000092/2025-2026 | 105/JSSD | 30/05/2025 | 14/07/2025 | GURUKUL INFOTECH | 4.97 | 0 | 0 | 0
13 | JALPAIGURI | Mal | Northern Mechanical | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/14883 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
14 | JALPAIGURI | Mal | Northern Mechanical | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/14883 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
Total | [13 empty] | 948.81 | 0 | 0