## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | Material Requisition To Resource Division |  |  | RTOR000061/2023-2024 | 1098/JD | 24/08/2023 | 24/08/2023 | Resource Division | 49.85 | 0 | 0 | 0
2 | JALPAIGURI | Mal | Jalpaiguri Division | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | Material Requisition To Resource Division |  |  | RTOR000141/2023-2024 | 1887/JD | 20/12/2023 | 20/12/2023 | Resource Division | 16.42 | 0 | 0 | 0
3 | JALPAIGURI | Mal | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for RANICHERA TG PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000673/2023-2024 | 1488/NMD | 17/08/2023 | 16/09/2023 | M/S PARITOSH BHOWMICK AND CO. | 37.96 | 0 | 0 | 70
4 | JALPAIGURI | Mal | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | Additional Works in connection with supply, installation, commissioning and trial operation of electro mechanical components along with copper own line voltage corrector for RANICHERA T.G PWSS in the Dist. of JALPAIGURI under Northern Mechanical Division PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000072/2024-2025 | 1061/HQ/NMD | 21/06/2024 | 28/06/2024 | M/S PARITOSH BHOWMICK AND CO. | 0.89 | 0 | 0 | 100
5 | JALPAIGURI | Mal | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | New Service Connection Charge for RANICHERA TEA GARDEN, T/W No. II, under ODLABARI CCC, [APPLICATION NO. 4003266404, Reference ID : 403105524] |  |  | BILL/01261/2023-2024 | 23-24/157&165 | 12/12/2023 | 12/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
6 | JALPAIGURI | Mal | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | Infrastructure Cost for RANICHERA TEA GARDEN, T/W No. II, under ODLABARI CCC, [APPLICATION NO. 100000093888, Reference ID : 860285548] |  |  | BILL/01262/2023-2024 | 23-24/157&165 | 12/12/2023 | 12/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.01 | 0 | 0 | 0
7 | JALPAIGURI | Mal | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | Infrastructure Cost for RANICHERA TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 100000093890, Reference ID : 860285650] |  |  | BILL/01264/2023-2024 | 23-24/157&165 | 12/12/2023 | 12/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.94 | 0 | 0 | 0
8 | JALPAIGURI | Mal | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | New Service Connection Charge for RANICHERA TG, TW NO-IV, OODLABARI CCC APPLICATION NO. 4003482909 Reference ID : 403269953 |  |  | BILL/01416/2024-2025 | BP/24-25/240 | 30/10/2024 | 30/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
9 | JALPAIGURI | Mal | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | New Service Connection Charge for RANICHERA TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 4003266407, Reference ID : 403105523] |  |  | BILL/01263/2023-2024 | 23-24/157&165 | 12/12/2023 | 12/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
10 | JALPAIGURI | Mal | Jalpaiguri Division | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  |  | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 07/03/2024 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
11 | JALPAIGURI | Mal | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | Infrastructure Cost for RANICHERA TEA GARDEN, T/W No. III, under ODLABARI CCC, [APPLICATION NO. 100000093887, Reference ID : 860285547] |  |  | BILL/01260/2023-2024 | 23-24/157&165 | 12/12/2023 | 12/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.25 | 0 | 0 | 0
12 | JALPAIGURI | Mal | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | New Service Connection Charge for RANICHERA TEA GARDEN, T/W No. III, under ODLABARI CCC, [APPLICATION NO. 4003266411, Reference ID : 403105529] |  |  | BILL/01259/2023-2024 | 23-24/157&165 | 12/12/2023 | 12/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
13 | JALPAIGURI | Mal | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | Infrastructure development cost for new service connection at RANICHERA TG, TW NO-IV, OODLABARI CCC APPLICATION NO. 100000117729 Reference ID : 860312409 |  |  | BILL/01415/2024-2025 | BP/24-25/240 | 30/10/2024 | 30/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.39 | 0 | 0 | 0
14 | JALPAIGURI | Mal | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
15 | JALPAIGURI | Mal | Jalpaiguri Division | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | Balance Laying Distribution System with providing Functional Household Tap Connection (FHTC) including sinking of One No Additional Tube Well by ODEX-165 method of drilling, construction of Pump House (3.60m x 2.40m) with sanitary plumbing arrangement, Boundary Wall and direct boosting for 5th site in the command area of Ranichera Tea Garden Piped Water Supply Scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000681/2024-2025 | 460/JD | 11/03/2025 | 31/07/2025 | GOEL CONSTRUCTION CO. | 80.53 | 0 | 0 | 90
16 | JALPAIGURI | Mal | Jalpaiguri Division | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | Construction of different components of Ranichera Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000175/2023-2024 | 845/JD | 28/07/2023 | 01/07/2025 | GOEL CONSTRUCTION CO. | 517.13 | 0 | 0 | 95
17 | JALPAIGURI | Mal | Jalpaiguri Division | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | Construction of Different balance component for Ranichera Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000823/2023-2024 | 2749/JD | 14/03/2024 | 01/07/2025 | GOEL CONSTRUCTION CO. | 86.19 | 0 | 0 | 100
Total | [13 empty] | 985.12 | 0 | 0