## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | Material Requisition To Resource Division |  |  | RTOR000061/2023-2024 | 1098/JD | 24/08/2023 |  | Resource Division | 49.85 | 0 | 0 | 0
2 | JALPAIGURI | Mal | Jalpaiguri Division | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | Material Requisition To Resource Division |  |  | RTOR000141/2023-2024 | 1887/JD | 20/12/2023 |  | Resource Division | 16.42 | 0 | 0 | 0
3 | JALPAIGURI | Mal | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | New Service Connection Charge for RANICHERA TEA GARDEN, T/W No. III, under ODLABARI CCC, [APPLICATION NO. 4003266411, Reference ID : 403105529] |  |  | BILL/01259/2023-2024 | 23-24/157&165 | 12/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
4 | JALPAIGURI | Mal | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | New Service Connection Charge for RANICHERA TEA GARDEN, T/W No. III, under ODLABARI CCC, [APPLICATION NO. 4003266411, Reference ID : 403105529] |  |  | BILL/01259/2023-2024 | 23-24/157&165 | 12/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
5 | JALPAIGURI | Mal | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | Infrastructure Cost for RANICHERA TEA GARDEN, T/W No. III, under ODLABARI CCC, [APPLICATION NO. 100000093887, Reference ID : 860285547] |  |  | BILL/01260/2023-2024 | 23-24/157&165 | 12/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.25 | 0 | 0 | 0
6 | JALPAIGURI | Mal | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | New Service Connection Charge for RANICHERA TEA GARDEN, T/W No. II, under ODLABARI CCC, [APPLICATION NO. 4003266404, Reference ID : 403105524] |  |  | BILL/01261/2023-2024 | 23-24/157&165 | 12/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
7 | JALPAIGURI | Mal | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | New Service Connection Charge for RANICHERA TEA GARDEN, T/W No. II, under ODLABARI CCC, [APPLICATION NO. 4003266404, Reference ID : 403105524] |  |  | BILL/01261/2023-2024 | 23-24/157&165 | 12/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
8 | JALPAIGURI | Mal | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | Infrastructure Cost for RANICHERA TEA GARDEN, T/W No. II, under ODLABARI CCC, [APPLICATION NO. 100000093888, Reference ID : 860285548] |  |  | BILL/01262/2023-2024 | 23-24/157&165 | 12/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.01 | 0 | 0 | 0
9 | JALPAIGURI | Mal | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | Infrastructure Cost for RANICHERA TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 100000093890, Reference ID : 860285650] |  |  | BILL/01264/2023-2024 | 23-24/157&165 | 12/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.94 | 0 | 0 | 0
10 | JALPAIGURI | Mal | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | New Service Connection Charge for RANICHERA TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 4003266407, Reference ID : 403105523] |  |  | BILL/01263/2023-2024 | 23-24/157&165 | 12/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
11 | JALPAIGURI | Mal | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | New Service Connection Charge for RANICHERA TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 4003266407, Reference ID : 403105523] |  |  | BILL/01263/2023-2024 | 23-24/157&165 | 12/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
12 | JALPAIGURI | Mal | Jalpaiguri Division | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  |  | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 |  | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
13 | JALPAIGURI | Mal | Jalpaiguri Division | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | Construction of Different balance component for Ranichera Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000823/2023-2024 | 2749/JD | 14/03/2024 | 13/04/2024 | GOEL CONSTRUCTION CO. | 86.19 | 37.27 | 43.24 | 60
14 | JALPAIGURI | Mal | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for RANICHERA TG PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000673/2023-2024 | 1488/NMD | 17/08/2023 | 16/09/2023 | M/S PARITOSH BHOWMICK AND CO. | 37.96 | 17.52 | 46.16 | 70
15 | JALPAIGURI | Mal | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | Additional Works in connection with supply, installation, commissioning and trial operation of electro mechanical components along with copper own line voltage corrector for RANICHERA T.G PWSS in the Dist. of JALPAIGURI under Northern Mechanical Division PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000072/2024-2025 | 1061/HQ/NMD | 21/06/2024 | 28/06/2024 | M/S PARITOSH BHOWMICK AND CO. | 0.89 | 0.44 | 49.36 | 100
16 | JALPAIGURI | Mal | Jalpaiguri Division | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000060/2024-2025 | 943/JD | 07/08/2024 | 22/08/2024 | GURUKUL INFOTECH | 4.83 | 0 | 0 | 0
17 | JALPAIGURI | Mal | Jalpaiguri Division | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 | New | Construction of different components of Ranichera Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000175/2023-2024 | 845/JD | 28/07/2023 | 24/01/2024 | GOEL CONSTRUCTION CO. | 517.13 | 334.96 | 64.77 | 95
Total | [13 empty] | 766.22 | 390.19 | 50.92