## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14886 | New | Material Requisition To Resource Division |  |  | RTOR000067/2023-2024 | 1072/JD | 24/08/2023 | 24/08/2023 | Resource Division | 27.2 | 0 | 0 | 0
2 | JALPAIGURI | Mal | Jalpaiguri Division | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14886 | New | Material Requisition To Resource Division |  |  | RTOR000157/2023-2024 | 2021/JD | 09/01/2024 | 09/01/2024 | Resource Division | 8.08 | 0 | 0 | 0
3 | JALPAIGURI | Mal | Northern Mechanical | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14886 | New | New Service Connection Charge for WASHABARI TG, TW NO-I, OODLABARI CCC APPLICATION NO. 4003460294 Reference ID : 403254628 |  |  | BILL/00624/2024-2025 | BP/24-25/156 | 06/08/2024 | 06/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
4 | JALPAIGURI | Mal | Northern Mechanical | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14886 | New | Infrastructure development cost for new service connection at WASHABARI TG, TW NO-II, OODLABARI CCC APPLICATION NO. 100000114552 Reference ID : 860309142 |  |  | BILL/00621/2024-2025 | BP/24-25/156 | 06/08/2024 | 06/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.95 | 0 | 0 | 0
5 | JALPAIGURI | Mal | Northern Mechanical | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14886 | New | Infrastructure development cost for new service connection at WASHABARI TG, TW NO-I, OODLABARI CCC APPLICATION NO. 100000114551 Reference ID : 860309141 |  |  | BILL/00623/2024-2025 | BP/24-25/156 | 06/08/2024 | 06/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.94 | 0 | 0 | 0
6 | JALPAIGURI | Mal | Northern Mechanical | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14886 | New | New Service Connection Charge for WASHABARI TG, TW NO-II, OODLABARI CCC APPLICATION NO. 4003460295 Reference ID : 403254629 |  |  | BILL/00622/2024-2025 | BP/24-25/156 | 06/08/2024 | 06/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
7 | JALPAIGURI | Mal | Jalpaiguri Division | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14886 | New | Construction of different components of Washabari Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000115/2023-2024 | 395/A/JD | 05/06/2023 | 26/09/2025 | S.S. CONSTRUCTION | 269.38 | 0 | 0 | 65
8 | JALPAIGURI | Mal | Northern Mechanical | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14886 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for WASHABARI TG PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000416/2023-2024 | 1330/NMD | 08/08/2023 | 01/09/2025 | SANJIB SAHA | 24.81 | 7.61 | 30.68 | 50
9 | JALPAIGURI | Mal | Northern Mechanical | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14886 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
10 | JALPAIGURI | Mal | Northern Mechanical | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14886 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
11 | JALPAIGURI | Mal | Jalpaiguri Division | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14886 | New | Sinking of Big Dia Tube well by Modified DTH - ODEX Method at 3rd & 4th tube well site of Washabari Tea Garden Piped Water Supply Scheme of Mal Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000440/2024-2025 | 2317/JD | 11/12/2024 | 10/01/2025 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 35.23 | 0 | 0 | 100
12 | JALPAIGURI | Mal | Jalpaiguri Division | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14886 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000060/2024-2025 | 943/JD | 07/08/2024 | 11/12/2025 | GURUKUL INFOTECH | 4.83 | 0 | 0 | 100
Total | [13 empty] | 871.24 | 7.61 | 0.87