## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | KHAS JANGAL PIPED WATER SUPPLY SCHEME | SM/14907 | New | Material Requisition To Resource Division |  |  | RTOR000066/2023-2024 | 1082/JD | 24/08/2023 | 24/08/2023 | Resource Division | 8.97 | 0 | 0 | 0
2 | JALPAIGURI | Mal | Jalpaiguri Division | KHAS JANGAL PIPED WATER SUPPLY SCHEME | SM/14907 | New | Material Requisition To Resource Division |  |  | RTOR000156/2023-2024 | 2024/JD | 09/01/2024 | 09/01/2024 | Resource Division | 2.81 | 0 | 0 | 0
3 | JALPAIGURI | Mal | Jalpaiguri Division | KHAS JANGAL PIPED WATER SUPPLY SCHEME | SM/14907 | New | Construction of different components of Khasjangal-I PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, BW, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block Mal under Jalpaiguri Division. | Assistant Engineer | Junior Engineer | ORD/000257/2023-2024 | 942/JD | 08/08/2023 | 29/07/2025 | A. K. INDUSTRIES | 133.2 | 0 | 0 | 30
4 | JALPAIGURI | Mal | Northern Mechanical | KHAS JANGAL PIPED WATER SUPPLY SCHEME | SM/14907 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KHAS JANGAL PWSS, TW No I AND II in the district of JALPAIGURI under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000659/2023-2024 | 1473/NMD | 17/08/2023 | 01/07/2025 | NIRMAN | 25.2 | 0 | 0 | 50
5 | JALPAIGURI | Mal | Northern Mechanical | KHAS JANGAL PIPED WATER SUPPLY SCHEME | SM/14907 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
6 | JALPAIGURI | Mal | Northern Mechanical | KHAS JANGAL PIPED WATER SUPPLY SCHEME | SM/14907 | New | Installation of two tank chlorination system at P.H No.-I under KHAS JANGAL PWSS of JJM in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001062/2024-2025 | 112/HQ/NMD | 17/01/2025 | 24/01/2025 | SARKAR ELECTRIC | 0.16 | 0 | 0 | 0
Total | [13 empty] | 302.68 | 0 | 0