## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | KHAS JANGAL PIPED WATER SUPPLY SCHEME | SM/14907 | New | Construction of different components of Khasjangal-I PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, BW, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block Mal under Jalpaiguri Division. | Assistant Engineer | Junior Engineer | ORD/000257/2023-2024 | 942/JD | 08/08/2023 | 04/02/2024 | A. K. INDUSTRIES | 133.2 | 0 | 0 | 0
2 | JALPAIGURI | Mal | Northern Mechanical | KHAS JANGAL PIPED WATER SUPPLY SCHEME | SM/14907 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KHAS JANGAL PWSS, TW No I AND II in the district of JALPAIGURI under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000659/2023-2024 | 1473/NMD | 17/08/2023 | 16/09/2023 | NIRMAN | 25.2 | 0 | 0 | 0
3 | JALPAIGURI | Mal | Jalpaiguri Division | KHAS JANGAL PIPED WATER SUPPLY SCHEME | SM/14907 | New | Material Requisition To Resource Division |  |  | RTOR000066/2023-2024 | 1082/JD | 24/08/2023 |  | Resource Division | 8.97 | 0 | 0 | 0
4 | JALPAIGURI | Mal | Jalpaiguri Division | KHAS JANGAL PIPED WATER SUPPLY SCHEME | SM/14907 | New | Material Requisition To Resource Division |  |  | RTOR000156/2023-2024 | 2024/JD | 09/01/2024 |  | Resource Division | 2.81 | 0 | 0 | 0
Total | [13 empty] | 170.18 | 0 | 0