## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME | SM/14908 | New | Material Requisition To Resource Division |  |  | RTOR000005/2023-2024 | 149/JD | 28/04/2023 | 28/04/2023 | Resource Division | 13.53 | 0 | 0 | 0
2 | JALPAIGURI | Mal | Jalpaiguri Division | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME | SM/14908 | New | Material Requisition To Resource Division |  |  | RTOR000153/2023-2024 | 2011/JD | 09/01/2024 | 09/01/2024 | Resource Division | 2.64 | 0 | 0 | 0
3 | JALPAIGURI | Mal | Northern Mechanical | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME | SM/14908 | New | New Service Connection Charge for DAKSHIN KANTADIGHI KUMARPARA, TW NO-I, MAL CCC APPLICATION NO. 4003352329 Reference ID : 403172831 |  |  | BILL/00197/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
4 | JALPAIGURI | Mal | Northern Mechanical | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME | SM/14908 | New | Infrastructure development cost for new service connection at DAKSHIN KANTADIGHI KUMARPARA, TW NO-II, MAL CCC APPLICATION NO. 100000102151 Reference ID : 860294701 |  |  | BILL/00200/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.83 | 0 | 0 | 0
5 | JALPAIGURI | Mal | Northern Mechanical | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME | SM/14908 | New | New Service Connection Charge for DAKSHIN KANTADIGHI KUMARPARA, TW NO-II, MAL CCC APPLICATION NO. 4003352331 Reference ID : 403172836 |  |  | BILL/00199/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
6 | JALPAIGURI | Mal | Northern Mechanical | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME | SM/14908 | New | Infrastructure development cost for new service connection at DAKSHIN KANTADIGHI KUMARPARA, TW NO-I, MAL CCC APPLICATION NO. 100000102150 Reference ID : 860294700 |  |  | BILL/00198/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.3 | 0 | 0 | 0
7 | JALPAIGURI | Mal | Jalpaiguri Division | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME | SM/14908 | New | Construction of Different Components of Dakshin Kantadighi Kumarpara PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, BW, Rising Main, FHTC etc. i.c.w. Jal Jeevan Mission at Block- Mal under | Assistant Engineer | Junior Engineer | ORD/000468/2022-2023 | 754/JD | 24/03/2023 | 18/06/2025 | B RAI CONSTRUCTION COMPANY | 134.73 | 0 | 0 | 50
8 | JALPAIGURI | Mal | Northern Mechanical | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME | SM/14908 | New | Installation of two tank chlorination system at different water supply scheme of JJM under Mal Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001002/2024-2025 | 55/HQ/NMD | 06/01/2025 | 13/01/2025 | SARKAR ELECTRIC | 0.95 | 0 | 0 | 0
9 | JALPAIGURI | Mal | Northern Mechanical | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME | SM/14908 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
10 | JALPAIGURI | Mal | Northern Mechanical | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME | SM/14908 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
11 | JALPAIGURI | Mal | Northern Mechanical | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME | SM/14908 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DAKSHIN KANTADIGHI KUMARPARA PWSS, TW No I AND II in the district of JALPAIGURI under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000309/2023-2024 | 1274/NMD | 02/08/2023 | 01/02/2025 | GOENKA ENTERPRISE | 24.41 | 0 | 0 | 80
Total | [13 empty] | 675.22 | 0 | 0