## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14911 | New | Material Requisition To Resource Division |  |  | RTOR000068/2023-2024 | 1073/JD | 24/08/2023 | 24/08/2023 | Resource Division | 17.26 | 0 | 0 | 0
2 | JALPAIGURI | Mal | Northern Mechanical | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14911 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for NIDAM JHORA TEA GARDEN PWSS, TW No I AND II in the district of JALPAIGURI under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000351/2023-2024 | 1312/NMD | 04/08/2023 | 01/10/2025 | MERCURY ENGINEERING COMPANY | 24.55 | 0 | 0 | 70
3 | JALPAIGURI | Mal | Jalpaiguri Division | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14911 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
4 | JALPAIGURI | Mal | Jalpaiguri Division | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14911 | New | Sinking of 1 (One) No Big Dia (200mm x 150mm) Tube Well by Modified DTH - ODEX Method of drilling at Nidam Jhora Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000587/2023-2024 | 2334/JD | 08/02/2024 | 23/02/2024 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 16.63 | 16.9 | 101.6 | 100
5 | JALPAIGURI | Mal | Jalpaiguri Division | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14911 | New | Material Requisition To Resource Division |  |  | RTOR000158/2023-2024 | 2023/JD | 09/01/2024 | 09/01/2024 | Resource Division | 3.63 | 0 | 0 | 0
6 | JALPAIGURI | Mal | Northern Mechanical | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14911 | New | Infrastructure development cost for new service connection at NIDAM JHORA TG, TW NO-I & II, MAL CCC APPLICATION NO. 100000104805 Reference ID : 860297125 |  |  | BILL/00180/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.19 | 0 | 0 | 0
7 | JALPAIGURI | Mal | Northern Mechanical | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14911 | New | New Service Connection Charge for NIDAM JHORA TG, TW NO-I, MAL CCC APPLICATION NO. 4003299874 Reference ID : 403130047 |  |  | BILL/00179/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
8 | JALPAIGURI | Mal | Northern Mechanical | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14911 | New | New Service Connection Charge for NIDAM JHORA TG, TW NO-II, MAL CCC APPLICATION NO. 4003299885 Reference ID : 403130043 |  |  | BILL/00181/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
9 | JALPAIGURI | Mal | Jalpaiguri Division | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14911 | New | Construction of different components of Nidam Jhora Tea Garden Pwss i.e TW, Pump House, Water Distribution Network,OHR, BW, Rising Main, FHTC etc. i.c.w Jal Jeevan mission at Block - Mal under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000258/2023-2024 | 943/JD | 08/08/2023 | 01/04/2025 | J.M. CONSTRUCTION | 138.12 | 60.56 | 43.85 | 80
10 | JALPAIGURI | Mal | Northern Mechanical | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14911 | New | Installation of two tank chlorination system at different water supply scheme of JJM under Mal Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001002/2024-2025 | 55/HQ/NMD | 06/01/2025 | 13/01/2025 | SARKAR ELECTRIC | 0.95 | 0 | 0 | 0
11 | JALPAIGURI | Mal | Northern Mechanical | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14911 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
12 | JALPAIGURI | Mal | Northern Mechanical | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14911 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
Total | [13 empty] | 726.8 | 77.46 | 10.66