## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Maynaguri | Jalpaiguri Division | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME | SM/14919 | New | Material Requisition To Resource Division |  |  | RTOR000026/2023-2024 | 170/JD | 28/04/2023 | 28/04/2023 | Resource Division | 15.65 | 0 | 0 | 0
2 | JALPAIGURI | Maynaguri | Northern Mechanical | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME | SM/14919 | New | New Service Connection Charge for UTTAR MARICHBARI MAYNAGURI, T/W I, under MAYNAGURI CCC, [APPLICATION NO. 4003164169, Reference ID : 403024436] |  |  | BILL/01065/2023-2024 | BP/23-24/104 | 30/09/2023 | 30/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3 | JALPAIGURI | Maynaguri | Northern Mechanical | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME | SM/14919 | New | Infrastructure Cost for UTTAR MARICH BARI MAYNAGURI, T/W II, under MAYNAGURI CCC, [APPLICATION NO. 100000084433, Reference ID : 860276013] |  |  | BILL/00581/2023-2024 | BP/23-24/72 | 09/08/2023 | 09/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.09 | 0 | 0 | 0
4 | JALPAIGURI | Maynaguri | Northern Mechanical | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME | SM/14919 | New | Infrastructure Cost for UTTAR MARICHBARI MAYNAGURI, T/W I, under MAYNAGURI CCC, [APPLICATION NO. 100000088138, Reference ID : 860278838] |  |  | BILL/01066/2023-2024 | BP/23-24/104 | 30/09/2023 | 30/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 19.26 | 0 | 0 | 0
5 | JALPAIGURI | Maynaguri | Northern Mechanical | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME | SM/14919 | New | New Service Connection Charge for UTTAR MARICH BARI MAYNAGURI, T/W II, under MAYNAGURI CCC, [APPLICATION NO. 4003164173, Reference ID : 403024437] |  |  | BILL/00580/2023-2024 | BP/23-24/72 | 09/08/2023 | 09/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
6 | JALPAIGURI | Maynaguri | Jalpaiguri Division | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME | SM/14919 | New | Construction of different components of Uttar Marichbari PWSS i.e, TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC, etc. in connection with Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000501/2022-2023 | 773/JD | 27/03/2023 | 06/03/2025 | UNIBRO INFRASERV PRIVATE LIMITED | 182.48 | 0 | 0 | 80
7 | JALPAIGURI | Maynaguri | Northern Mechanical | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME | SM/14919 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for UTTAR MARICHBARI PWSS, TW no I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000431/2023-2024 | 1370/NMD | 09/08/2023 | 01/09/2024 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 20.62 | 0 | 0 | 100
8 | JALPAIGURI | Maynaguri | Jalpaiguri Division | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME | SM/14919 | New | Construction of Boundary Wall at 2nd Pump House site including raising main and interconnection of Uttar Marichbari PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000673/2023-2024 | 166/RWS | 15/02/2024 | 16/03/2024 | PINTU DAS | 6.14 | 0 | 0 | 100
9 | JALPAIGURI | Maynaguri | Jalpaiguri Division | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME | SM/14919 | New | Material Requisition To Resource Division |  |  | RTOR000181/2023-2024 | 2046/JD | 09/01/2024 | 09/01/2024 | Resource Division | 5.49 | 0 | 0 | 0
10 | JALPAIGURI | Maynaguri | Jalpaiguri Division | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME | SM/14919 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  |  | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 03/04/2024 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
11 | JALPAIGURI | Maynaguri | Jalpaiguri Division | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME | SM/14919 | New | Construction of Boundary Wall at H/W site including rising main and interconnections of Uttar Marichbari PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000565/2023-2024 | 2174/JD | 22/01/2024 | 01/12/2025 | SUBRATA GOSWAMI | 15.52 | 0 | 0 | 100
12 | JALPAIGURI | Maynaguri | Northern Mechanical | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME | SM/14919 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000002/2025-2026 | 961/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0 | 0
13 | JALPAIGURI | Maynaguri | Northern Mechanical | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME | SM/14919 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
14 | JALPAIGURI | Maynaguri | Jalpaiguri Division | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME | SM/14919 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-C of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000070/2024-2025 | 985/JD | 14/08/2024 | 29/08/2024 | LIMRA SOCIAL WELFARE SOCIETY | 4.63 | 0 | 0 | 100
Total | [13 empty] | 766.86 | 0 | 0