## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | Providing Functional Household Tap connection (FHTC) at Paharer Hat in connection with JJM at Arji Garalbari Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P.H.E. Dte.(Part-I) | Assistant Engineer | Junior Engineer | ORD/000420/2022-2023 | 600/JD | 09/03/2023 | 30/03/2023 | RANJIT KARMAKAR | 4.85 | 4.82 | 99.46 | 100
2 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | Construction of Pump House (3.60M X 2.40M) Size with sanitary & plumbing arrangement including Boundary wall, drain and pathway for 3rd Tubewell site of Arji Garalbari Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000379/2022-2023 | 169/JD | 19/01/2023 | 18/02/2023 | ABHIJIT SARKAR | 10.88 | 10.82 | 99.42 | 100
3 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | Retrofitting works related to FHTC at Barokamat, Dhaurapara for Argi Garalbari W/S Scheme under Jalpaiguri Division, PHE Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000040/2023-2024 | 392/RWS | 25/04/2023 | 09/05/2023 | BISWAJIT BHADURI | 3.54 | 3.53 | 99.74 | 100
4 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | New Service Connection Charge for ARJI GARALBARI (REJU), T/W IV, under PANDAPARA CCC [APPLICATION NO. 4003103534 ; Reference ID : 402988696] |  |  | BILL/00006/2023-2024 | BP/23-24/33 | 09/06/2023 | 09/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | Infrastructure Cost for ARJI GARALBARI (REJU), T/W IV, under PANDAPARA CCC [APPLICATION NO. 100000075210 ; Reference ID : 860266620] |  |  | BILL/00493/2023-2024 |  | 23/06/2023 | 23/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.97 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | Infrastructure Cost for ARJI GARALBARI (REJU), T/W IV, under PANDAPARA CCC [APPLICATION NO. 100000075210 ; Reference ID : 860266620] |  |  | BILL/00007/2023-2024 | BP/23-24/47 | 04/07/2023 | 04/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.97 | 0 | 0 | 0
7 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | New Service Connection Charge for ARGI GARALBARI, T/W III, under PANDAPARA CCC [APPLICATION NO. 4003099007 ; Reference ID : 402983422] |  |  | BILL/00520/2023-2024 | BP/23-24/115 | 06/10/2023 | 06/10/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
8 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | Infrastructure Cost for ARGI GARALBARI, T/W III, under PANDAPARA CCC [APPLICATION NO. 100000074333 ; Reference ID : 860264763] |  |  | BILL/00521/2023-2024 | BP/23-24/115 | 06/10/2023 | 06/10/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.03 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | Rising Main Connections(at 3rd TW site) including other necessary arrangement for Rejuvenation of Araji Garalbari Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte Jalpaiguri. | Assistant Engineer | Junior Engineer | ORD/000490/2022-2023 | 289/RWS | 29/03/2023 | 12/04/2023 | ALICK DATTA | 1.81 | 1.79 | 98.99 | 100
10 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | Construction of different components for Rejuvenation of Arji Garalbari PWSS i.e. TW, Pump Houses, IEP, Boundary Walls, Rising Main etc. in connection with Jal Jeevan Mission at Block - Jalpaiguri sadar under Jalpaiguri Division, P.H.E.Dte | Assistant Engineer | Junior Engineer | ORD/000109/2023-2024 | 434/JD. | 08/06/2023 | 27/12/2024 | ASIM GUPTA | 40.15 | 9.44 | 23.51 | 40
11 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF ARJI GARALBARI Piped Water Supply Scheme, TW No.- III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000133/2023-2024 | 812/NMD | 20/07/2023 | 19/08/2023 | M/S ANJALI ENTERPRISE | 11.53 | 11.5 | 99.79 | 100
12 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF ARJI GARALBARI PWSS,at TW NO IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000134/2023-2024 | 813/NMD | 20/07/2023 | 19/08/2023 | SARKAR ELECTRIC | 11.71 | 11.71 | 100 | 100
13 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | Supply, Installation, Commissioning (Trial run for 3 months) including testing of 15.00 cum per hour capacity pressure type IEP with accessories including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd tube well site for Rejuvenation of Araji Garalbari water supply scheme under Jalpaiguri Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000255/2023-2024 | 941/JD | 08/08/2023 | 22/09/2023 | LOKNATH CONSTRUCTION | 17.31 | 17.24 | 99.59 | 100
14 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000986/2024-2025 | 10/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0 | 0
15 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
Total | [13 empty] | 724.45 | 70.86 | 9.78