## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF HASLURDANGA PIPED WATER SUPPLY SCHEME | SM/15031 | Augmentation | Construction of different components of Rejuvination of Haslurdanga PWSS i.e. TW, Pump Houses, Water distribution Network , Boundary wall , RISING MAIN , etc. in connection with JJM at Block - Maynaguri under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000073/2023-2024 | 388/A/JD | 01/06/2023 | 09/01/2025 | BISWAJIT BHADURI | 82.64 | 59.81 | 72.37 | 100
2 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF HASLURDANGA PIPED WATER SUPPLY SCHEME | SM/15031 | Augmentation | Retro fitting works due to FHTC in connection for JJM under the command area of Huslu Danga piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000435/2022-2023 | 675/JD | 16/03/2023 | 31/03/2023 | M/S ROY & SARKAR CONSTRUCTION | 2.92 | 2.92 | 100 | 0
3 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF HASLURDANGA PIPED WATER SUPPLY SCHEME | SM/15031 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF HASLURDANGA PWSS, TW no III and IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000443/2023-2024 | 1382/NMD | 09/08/2023 | 08/09/2023 | BLUE PINE | 20.22 | 20.2 | 99.94 | 100
4 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF HASLURDANGA PIPED WATER SUPPLY SCHEME | SM/15031 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000102/2023-2024 | 1048/JD | 24/08/2023 | 24/08/2023 | Resource Division | 4.8 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF HASLURDANGA PIPED WATER SUPPLY SCHEME | SM/15031 | Augmentation | Supply and Delivery of C.I special as when as required at T/W No-I of HASLUDANGA and other adjacent W/S Scheme under in the Dist. of JALPAIGURI. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000067/2024-2025 | 1056/HQ/NMD | 21/06/2024 | 28/06/2024 | B.B. CONCERNED | 0.73 | 0.39 | 52.96 | 100
6 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF HASLURDANGA PIPED WATER SUPPLY SCHEME | SM/15031 | Augmentation | New Service Connection Charge for HUSLUDANGA, T/W-IV under MAYNAGURI CCC APPLICATION NO. 4003356517 Reference ID : 403175891 |  |  | BILL/00188/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.84 | 0 | 0 | 0
7 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF HASLURDANGA PIPED WATER SUPPLY SCHEME | SM/15031 | Augmentation | New Service Connection Charge for HUSLUDANGA, T/W-III under MAYNAGURI CCC APPLICATION NO. 4003356512 Reference ID : 403175904 |  |  | BILL/00187/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.32 | 0 | 0 | 0
8 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF HASLURDANGA PIPED WATER SUPPLY SCHEME | SM/15031 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000002/2025-2026 | 961/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0 | 0
9 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF HASLURDANGA PIPED WATER SUPPLY SCHEME | SM/15031 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
Total | [13 empty] | 575.65 | 83.32 | 14.47