## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Bhangarhat Piped Water Supply Scheme | SM/15032 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF BHANGARHAT PWSS, TW NO- I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000183/2023-2024 | 1220/NMD | 26/07/2023 | 01/03/2025 | GURUKRIPA ENTERPRISE | 11.5 | 0 | 0 | 80
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Bhangarhat Piped Water Supply Scheme | SM/15032 | Augmentation | Construction of Pump House, Sinking Tube Well, Laying Rising Main etc of Bhangarhat PWSS , in connection with Rejuvenation of Bhangarhat PWSS under Jal Jeevan Mission at Maynaguri Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000098/2023-2024 | 349/JD | 24/05/2023 | 19/05/2025 | DIPAK KUMAR CHAKRABORTY | 36.26 | 15.1 | 41.63 | 100
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Bhangarhat Piped Water Supply Scheme | SM/15032 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000100/2023-2024 | 1053/JD | 24/08/2023 | 24/08/2023 | Resource Division | 2.59 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Bhangarhat Piped Water Supply Scheme | SM/15032 | Augmentation | Laying distribution system for balanced DI pipeline from Ranirhat More towards Dhupguri for Bhangarhat PWSS at Maynaguri Block under Jalapaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000734/2023-2024 | 2454/JD | 23/02/2024 | 08/03/2024 | DIPAK KUMAR CHAKRABORTY | 11.62 | 11.9 | 102.4 | 100
5 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Bhangarhat Piped Water Supply Scheme | SM/15032 | Augmentation | Construction of Boundary Wall footpath, drain, land development at 4th Tubewell site including providing FHTC in the command area of Bhangarhat PWSS in connection with Jal Jeevan Mission at Block Maynaguri under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000141/2024-2025 | 1528/JD | 01/10/2024 | 01/07/2025 | DIPAK KUMAR CHAKRABORTY | 14.57 | 0 | 0 | 50
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Bhangarhat Piped Water Supply Scheme | SM/15032 | Augmentation | New Service Connection Charge for REJUVENATION OF BHANGARHAT, T/W-I under MAYNAGURI CCC APPLICATION NO. 4003376107 Reference ID : 403191657 |  |  | BILL/00153/2024-2025 | BP/24-25/25 | 09/05/2024 | 09/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.2 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Bhangarhat Piped Water Supply Scheme | SM/15032 | Augmentation | Balance Laying Distribution System including Providing FHTC and other allied work related to pipe line at Bhangerhat PWSS in connection with Jal Jeevan Mission at Block Dhupguri under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000450/2024-2025 | 103/JD | 15/01/2025 | 11/11/2025 | ARATI CONSTRUCTION | 34.03 | 0 | 0 | 0
8 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Bhangarhat Piped Water Supply Scheme | SM/15032 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
Total | [13 empty] | 475.89 | 26.99 | 5.67