## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Chauhaddi Piped Water Supply Scheme | SM/15033 | Augmentation | New Service Connection Charge for REJUVENATION OF CHAUHADDI PWSS, TW NO IV, under DHUPGURI CCC APPLICATION NO. 4003460809 Reference ID : 403255219 |  |  | BILL/00970/2024-2025 | BP/24-25/166 | 14/08/2024 | 14/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.39 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme | SM/15033 | Augmentation | Laying of Rising Main/Direct Boosting Line for The Rejuvenation of Purba Magurmari P.W.S.S and Rejuvenation of Chouhaddi P.W.S.S. along with FHTC(PhaseVII) within the command area of Rejuventaion of Purba Magurmari P.W.S.S. in connection with Jal Jeevan Mission under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000397/2023-2024 | 1587/JD | 06/11/2023 | 01/11/2025 | SAHA CONSTRUCTION | 37.11 | 0 | 0 | 30
3 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Chauhaddi Piped Water Supply Scheme | SM/15033 | Augmentation | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Driller-in-Charge |  | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 25/03/2025 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme | SM/15033 | Augmentation | Construction of different components of Rejuvenation Chauhaddi PWSS i.e. TW, Pump Houses, Water distribution Network, , RISING MAIN etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,Assistant Engineer,HQ | Junior Engineer | ORD/000100/2023-2024 | 350/JD | 24/05/2023 | 22/06/2024 | HARIPADA BANERJEE | 61.11 | 0 | 0 | 100
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Chauhaddi Piped Water Supply Scheme | SM/15033 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF CHAUHADDI PWSS at TW No. IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000290/2024-2025 | 1637/NMD | 25/09/2024 | 01/04/2025 | SUMON ELECTRICAL | 11.73 | 0 | 0 | 80
Total | [13 empty] | 117.8 | 0 | 0