## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme | SM/15059 | Augmentation | Providing Functional Household Tap Connection in connection with Jaldhara/Jalswapna near factory line and allied areas for Barodighi TG Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000387/2022-2023 | 362/JD | 20/02/2023 | 06/03/2023 | PRIYABRATA KARMAKAR | 6.38 | 6.37 | 99.98 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme | SM/15059 | Augmentation | Providing Functional Household Tap Connection (150 nos) in connection with JJM near Dipu line, Mangla line, Bhouka line and allied areas for Barodighi T.G. Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000351/2022-2023 | 613/JD | 09/03/2023 | 24/03/2023 | PRIYABRATA KARMAKAR | 7.12 | 7.05 | 98.96 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme | SM/15059 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000058/2023-2024 | 1089/JD | 24/08/2023 | 24/08/2023 | Resource Division | 5.42 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme | SM/15059 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF BARADIGHI PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000169/2023-2024 | 1211/NMD | 26/07/2023 | 25/08/2023 | ASHWIRBAD WOOD CRAFT | 11.45 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme | SM/15059 | Augmentation | Conctruction of approach road with paver block inside the premises and outside approach, R.B.T fixing in boundary wall and inside drain at H/W site for Barodighi TG Area Piped Water Supply Scheme under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer | Junior Engineer | ORD/000406/2022-2023 | 612/JD | 09/03/2023 | 30/03/2023 | BOSE ENTERPRISE | 13.4 | 13.34 | 99.58 | 100
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme | SM/15059 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BARADIGHI PWSS, TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000974/2023-2024 | 1896/NMD | 30/11/2023 | 30/12/2023 | S.P. ENTERPRISE | 11.3 | 11.23 | 99.42 | 100
7 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme | SM/15059 | Augmentation | New Service Connection Charge for BARADIGHI T/W No. I under MATELI CCC [APPLICATION NO. 4003279994 ; Reference ID :403115813] |  |  | BILL/01721/2023-2024 | BP/23-24/234 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
8 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme | SM/15059 | Augmentation | Infrastructure Cost for BARADIGHI T/W No. I under MATELI CCC [APPLICATION NO. 100000094585 ; Reference ID :860286265] |  |  | BILL/01722/2023-2024 | BP/23-24/235 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.51 | 0 | 0 | 0
9 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme | SM/15059 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: METELI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000883/2024-2025 | 24/NMD | 06/01/2025 | 05/02/2025 | EASTERN INDIA SALES & SERVICE | 15.33 | 0 | 0 | 0
10 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme | SM/15059 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (MATIALI Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000993/2024-2025 | 13/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 36.03 | 0 | 0 | 0
11 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme | SM/15059 | Augmentation | "New Service Connection Charge for BARADIGHI TG TW-III(Near scout club fouzi more) Application no-4003568378 Reference Id-403332166 |  |  | BILL/02199/2024-2025 | BP/24-25/250 | 21/01/2025 | 21/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
12 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme | SM/15059 | Augmentation | INFRA COST IRO DTR INSTALLATION FOR TW-III BARADIGHI TG(NEAR SCOUT CLUB FOUZI MORE) APPLICATION ID-100000127308 REFERENCE ID-860323108 |  |  | BILL/02198/2024-2025 | BP/24-25/250 | 21/01/2025 | 21/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.38 | 0 | 0 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme | SM/15059 | Augmentation | Construction of 250 cum capacity 20 m staging height OHR, tube well, pump house 3.60x2.40m with sanitary arrangement, boundary wall, Laying distribution system, Rising Main for BARADIGHI T.G. under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000042/2020-2021 | 1060/JD | 13/10/2020 | 02/04/2025 | BOSE ENTERPRISE | 126.27 | 0 | 0 | 100
14 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme | SM/15059 | Augmentation | Construction of different components of Rejuvenation of Baradighi Tea Garden PWSS i.e. TW, Pump Houses, Boundary Walls, Water Distribution Network, Rising Main etc. in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000110/2023-2024 | 404/A/JD | 06/06/2023 | 01/04/2026 | ALICK DUTTA | 32.52 | 10.25 | 31.53 | 50
Total | [13 empty] | 273.51 | 48.25 | 17.64