## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/15060 | Augmentation | Construction of different components of Rejuvenation of Nagaisuree Tea Garden PWSS i.e. 3rd Site Boundary Walls, Rising Main etc. in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E.Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000096/2023-2024 | 335/JD | 22/05/2023 | 21/06/2023 | BAJRANG ENTERPRISE | 7.79 | 7.73 | 99.31 | 100
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/15060 | Augmentation | Construction of different components of Rejuvenation of Nagaisuree Tea Garden PWSS i.e. 4th Site Boundary Walls, Rising Main etc. in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E.Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000293/2023-2024 | 1414/JD | 03/10/2023 | 02/11/2023 | ARUP SARKAR | 7.02 | 6.97 | 99.29 | 100
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/15060 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000093/2023-2024 | 1052/JD | 24/08/2023 | 24/08/2023 | Resource Division | 23.38 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/15060 | Augmentation | Sinking of 2 Nos. Big Dia Tube Well by Modified DTH - ODEX Method at Yong Tong Tea Gargen Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000016/2024-2025 | 532/JD | 28/06/2024 | 28/07/2024 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 33.23 | 0 | 0 | 100
5 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/15060 | Augmentation | Sinking of Big Dia Tube well by Modified DTH - ODEX Method at 5th & 6th tube well site of Nagaisuree Tea Garden Piped Water Supply Scheme of Matiali Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000108/2024-2025 | 1361/JD | 11/09/2024 | 11/10/2024 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 35.23 | 27.14 | 77.03 | 100
6 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/15060 | Augmentation | Providing Inspection Vehicle WB-71B-9586 for JJM on daily basis @12.00/Km for Official use of the Assistant Engineer, Jalpaiguri Sadar-Sub Division P.H.E. Dte (OCT 2023 TO DEC 2023) |  |  | BILL/01202/2023-2024 | BP-2023-24-637 | 09/02/2024 | 09/02/2024 | DHIRAJ BISWAS | 1.2 | 0 | 0 | 0
7 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/15060 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector at REJUVENATION OF NAGAISUREE TEA GARDEN PWSS for T/W No. V and VI in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000848/2024-2025 | 587/NMD | 07/02/2025 | 09/03/2025 | ALPHA ENTERPRISE | 27.14 | 0 | 0 | 0
8 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/15060 | Augmentation | Installation of two tank chlorination system at Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme(TW-I) and other adjacent water supply scheme UNDER JJM under METELI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000665/2025-2026 | 1084/HQ/NMD | 15/05/2025 | 22/05/2025 | D.K. & SONS | 0.79 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/15060 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000092/2024-2025 | 285/JD | 10/02/2025 | 10/02/2025 | Resource Division | 43.73 | 0 | 0 | 0
10 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/15060 | Augmentation | New service connection charge for Nagaisuree TG, TW-V (Tanti Line Ground Nagaisuree TG) Reference Id-403344368 Application no-4003584975 |  |  | BILL/02353/2024-2025 | BP/24-25/252 | 17/03/2025 | 17/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
11 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/15060 | Augmentation | New service connection charge for Nagaisuree TG, TW-VI(Bhusur Line Ground Nagaisuree TG) Reference Id-403344369 Application no-4003584969 |  |  | BILL/02351/2024-2025 | BP/24-25/252 | 17/03/2025 | 17/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
12 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/15060 | Augmentation | Deposite work other than service connection For Nagaisuree TG, TW-VI (Bhusur Line Nagaisuree TG) INFRA COST IRO DTR INSTALLATION Reference Id-860325173 Application no-100000130033 |  |  | BILL/02350/2024-2025 | BP/24-25/252 | 17/03/2025 | 17/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.52 | 0 | 0 | 0
13 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/15060 | Augmentation | service connection charge for NAGAISUREE TG TW-VI(BHUSUR LINE) Application no-4003618654 Reference Id-403371468 |  |  | BILL/00032/2025-2026 | 86/W/25-26 | 13/08/2025 | 13/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
14 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/15060 | Augmentation | Deposite work other than service connection For Nagaisuree TG, TW-V (Tanti Line Ground Nagaisuree TG) INFRA COST IRO DTR INSTALLATION Reference Id-860325172 Application no-100000130032 |  |  | BILL/02352/2024-2025 | BP/24-25/252 | 17/03/2025 | 17/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.48 | 0 | 0 | 0
Total | [13 empty] | 203.56 | 41.84 | 20.56