## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF JOGESH CHANDRA TEA GARDEN AREA PWSS | SM/15068 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000079/2023-2024 | 1061/JD | 24/08/2023 | 24/08/2023 | Resource Division | 1.25 | 0 | 0 | 0
2 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF JOGESH CHANDRA TEA GARDEN AREA PWSS | SM/15068 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF JOGESH CHANDRA TG AREA PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000428/2023-2024 | 1345/NMD | 08/08/2023 | 01/12/2024 | SAIKAT SINHA | 11.35 | 7.83 | 68.95 | 50
3 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF JOGESH CHANDRA TEA GARDEN AREA PWSS | SM/15068 | Augmentation | Infrastructure development cost for new service connection at Reju. of Jogeshchandra TG, TW NO-III, KRANTI CCC APPLICATION NO. 100000103458 Reference ID : 860295868 |  |  | BILL/00211/2024-2025 | BP/24-25/25 | 09/05/2024 | 09/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.46 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF JOGESH CHANDRA TEA GARDEN AREA PWSS | SM/15068 | Augmentation | New Service Connection Charge for Reju. of Jogeshchandra TG, TW NO-III, KRANTI CCC APPLICATION NO. 4003373903 Reference ID : 403190124 |  |  | BILL/00210/2024-2025 | BP/24-25/25 | 09/05/2024 | 09/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF JOGESH CHANDRA TEA GARDEN AREA PWSS | SM/15068 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF JOGESH CHANDRA TEA GARDEN AREA PWSS | SM/15068 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
Total | [13 empty] | 514.2 | 7.83 | 1.52