## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF RAIPUR TEA GARDEN AREA PWSS | SM/15071 | Augmentation | Land devlopment at 2nd site under Raipur T.G. Piped Water Supply Scheme under Jalpiaiguri Division,P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000494/2022-2023 | 286/RWS | 29/03/2023 | 08/04/2023 | NEW KUNDU ENTERPRISE | 0.98 | 0.98 | 99.88 | 100
2 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF RAIPUR TEA GARDEN AREA PWSS | SM/15071 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF RAIPUR TEA GARDEN PWSS,at TW NO III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000722/2023-2024 | 1544/NMD | 01/09/2023 | 01/10/2023 | SAIKAT SINHA | 12.42 | 8.62 | 69.45 | 100
3 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF RAIPUR TEA GARDEN AREA PWSS | SM/15071 | Augmentation | New Service Connection Charge for RAIPUR TEA GARDEN,T/W-III, under UKILPARA MASKALIBARI CCC APPLICATION NO. 4003343597 Reference ID : 403174733 |  |  | BILL/00161/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.87 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF RAIPUR TEA GARDEN AREA PWSS | SM/15071 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000986/2024-2025 | 10/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF RAIPUR TEA GARDEN AREA PWSS | SM/15071 | Augmentation | Construction of different components of Rejuvenation of Raipur T.G. PWSS i.e TW, pump houses,water distribution network, Boundary wall, Rising main, etc in connection with JJM at Block - Jalpaiguri Sadar under jalpaiguri Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000107/2023-2024 | 385/JD | 01/06/2023 | 01/03/2025 | NEW KUNDU ENTERPRISE | 49.45 | 36.51 | 73.83 | 100
Total | [13 empty] | 126.38 | 46.12 | 36.49