## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mogalkata Tea Garden Area Piped Water Supply Scheme | SM/15075 | Augmentation | Laying of Pipe line in uncovered area including installation of Sluice Valves at different strategic point within the command area of Mogolkata T.G. P.W.S.S. at Dhupguri Block under Jalpaiguri Division. P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000191/2022-2023 | 1694/JD | 06/09/2022 | 27/09/2022 | DIPAK KUMAR CHAKRABORTY | 4.1 | 4.11 | 100.17 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mogalkata Tea Garden Area Piped Water Supply Scheme | SM/15075 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000051/2023-2024 | 1099/JD | 24/08/2023 | 24/08/2023 | Resource Division | 2.59 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mogalkata Tea Garden Area Piped Water Supply Scheme | SM/15075 | Augmentation | Providing FHTC including retrofitting works near Totapara Bazar for Mogalkata Piped Water Supply Scheme at Banarhat Block in under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000539/2023-2024 | 1971/JD | 03/01/2024 | 23/01/2024 | JITENDRA NATH ROY | 12.57 | 9.73 | 77.38 | 100
4 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mogalkata Tea Garden Area Piped Water Supply Scheme | SM/15075 | Augmentation | New Service Connection Charge for REJUVENATION OF MOGALKATA TG, T/W-III, under BANARHAT CCC APPLICATION NO. 4003374000 Reference ID : 403189743 |  |  | BILL/00134/2024-2025 | BP/24-25/01 | 10/04/2024 | 10/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.02 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mogalkata Tea Garden Area Piped Water Supply Scheme | SM/15075 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (BANARHAT Block ) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000987/2024-2025 | 11/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 57.53 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mogalkata Tea Garden Area Piped Water Supply Scheme | SM/15075 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mogalkata Tea Garden Area Piped Water Supply Scheme | SM/15075 | Augmentation | Construction of Pump House, Sinking Tube Well, Laying Rising Main, Water Distribution Network etc. of Mogalkata Tea Garden PWSS , in connection with Rejuvenation of Mogalkata Tea Garden PWSS under Jal Jeevan Mission at Banarhat Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000133/2023-2024 | 411/A/JD | 07/06/2023 | 05/06/2025 | JAYA SARKAR | 27.08 | 18.59 | 68.62 | 100
8 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mogalkata Tea Garden Area Piped Water Supply Scheme | SM/15075 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF MOGALKATA TEA GARDEN AREA PWSS, TW NO III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000459/2023-2024 | 1435/NMD | 10/08/2023 | 01/10/2024 | SAIKAT SINHA | 11.5 | 8.99 | 78.12 | 100
Total | [13 empty] | 666.99 | 41.41 | 6.21