## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF PASCHIM SALBARI PWSS | SM/15076 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with JJM under the command area of Paschim Salbari (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000418/2022-2023 | 170/RWS | 28/02/2023 | 21/03/2023 | SAHA CONSTRUCTION | 4.91 | 4.51 | 91.75 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF PASCHIM SALBARI PWSS | SM/15076 | Augmentation | "Restoration of DI pipeline earlier damaged under Paschim Salbari Water Supply Scheme (Zone-1) under Jalpaiguri Division PHE Dte. " | Assistant Engineer | Junior Engineer 2 | ORD/000188/2022-2023 | 554/RWS | 01/09/2022 | 01/10/2022 | B.M CONSTRUCTION | 3.28 | 2.56 | 78.04 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF PASCHIM SALBARI PWSS | SM/15076 | Augmentation | Emergency repairing of pipe line damaged due to rural road construction and provision for laying of Gas pipe line at different location under Paschim Salbari (Zone - I) Water Supply Scheme under Jalpaiguri Division, PHE Dte. (2nd Call) | Assistant Engineer | Junior Engineer 2 | ORD/000148/2023-2024 | 812/RWS | 14/07/2023 | 04/08/2023 | SAHA CONSTRUCTION | 2.99 | 2.84 | 95.13 | 100
4 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF PASCHIM SALBARI PWSS | SM/15076 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF PASCHIM SALBARI PWSS, TW NO- I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000057/2023-2024 | 572/NMD | 17/05/2023 | 16/06/2023 | M/S JIT ENTERPRISE | 23.04 | 17.48 | 75.89 | 50
5 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF PASCHIM SALBARI PWSS | SM/15076 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with JJM under the command area of Paschim Salbari (Zone-II) Piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000486/2022-2023 | 284/RWS | 29/03/2023 | 19/04/2023 | PARAMJYOTI ENTERPRISE | 4.94 | 4.91 | 99.51 | 100
6 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF PASCHIM SALBARI PWSS | SM/15076 | Augmentation | Supply and Delivery of C.I special as when as required at T/W No-I of PASCHIM SALBARI and other adjacent W/S Scheme under in the Dist. of JALPAIGURI. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000070/2024-2025 | 1059/HQ/NMD | 21/06/2024 | 28/06/2024 | CHOWDHURY AND BASU ENTERPRISE | 0.73 | 0.73 | 100 | 100
7 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF PASCHIM SALBARI PWSS | SM/15076 | Augmentation | New Service Connection Charge for Reju. of Paschim Salbari, T/W-II under BHOTPATTY CCC APPLICATION NO. 4003531577 Reference ID : 403306437 |  |  | BILL/01466/2024-2025 | BP/24-25/246 | 02/12/2024 | 02/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.65 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF PASCHIM SALBARI PWSS | SM/15076 | Augmentation | Construction of different components for Rejuvenation of Paschim Salbari PWSS i.e. TW, Pump Houses, Water distribution Network, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000039/2023-2024 | 129/JD | 28/04/2023 | 01/05/2025 | NARAYAN CHANDRA SAHA | 112.5 | 0 | 0 | 50
9 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF PASCHIM SALBARI PWSS | SM/15076 | Augmentation | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000776/2024-2025 | 290/HQ/NMD | 24/01/2025 | 23/02/2025 | S.P. ENTERPRISE | 2 | 0 | 0 | 0
10 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF PASCHIM SALBARI PWSS | SM/15076 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000002/2025-2026 | 961/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0 | 0
11 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF PASCHIM SALBARI PWSS | SM/15076 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
12 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF PASCHIM SALBARI PWSS | SM/15076 | Augmentation | New Service Connection Charge for Reju. of Paschim Salbari, T/W-I under MAYNAGURI CCC APPLICATION NO. 4003550068 Reference ID : 403320233 |  |  | BILL/01676/2024-2025 | BP/24-25/249 | 13/12/2024 | 13/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.66 | 0 | 0 | 0
Total | [13 empty] | 617.88 | 33.04 | 5.35