## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15077 | Augmentation | Construction of different components of Rejuvenation of Songachi T.G. PWSS i.e pump houses, water distribution network, Boundary wall, Rising main, FHTC etc. in connection with JJM at Block - Matiali under jalpaiguri Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000088/2023-2024 | 441/JD. | 08/06/2023 | 07/08/2023 | PINAKI MITRA | 34.93 | 5.56 | 15.91 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15077 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000095/2023-2024 | 1049/JD | 24/08/2023 |  | Resource Division | 2.45 | 0 | 0 | 0
3 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15077 | Augmentation | New Service Connection Charge for SOONGACHI TEA GARDEN (REJU), T/W III, under MAL CCC, [APPLICATION NO. 4003220150, Reference ID : 403066255] |  |  | BILL/01071/2023-2024 | BP/23-24/107 | 30/09/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15077 | Augmentation | Infrastructure Cost for SOONGACHI TEA GARDEN (REJU), T/W III, under MAL CCC, [APPLICATION NO. 100000088108, Reference ID : 860279669] |  |  | BILL/01072/2023-2024 | BP/23-24/107 | 30/09/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.96 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15077 | Augmentation | FUEL BILL |  |  | BILL/00631/2023-2024 | BP-2023-24-433 | 11/10/2023 |  | FILL & SMILE | 0.53 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15077 | Augmentation | Construction of deep tube well by ODEX-195 method of drilling for Songachi T.G. Piped Water Supply Scheme, Block- Matiali, Dist- Jalpaiguri. | Assistant Engineer | Junior Engineer | ORD/000195/2022-2023 | 1592/JD | 17/08/2022 | 07/09/2022 | R.S CONSTRUCTION | 9.32 | 3.88 | 41.64 | 100
7 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15077 | Augmentation | Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer Jalpaiguri R.W.S Sub-Division P.H.E. Dte. Jalpaiguri for 6 month (Period from 01.08.2023 to 31.01.2024) |  |  | ORD/000268/2023-2024 | 877/RWS | 31/07/2023 | 27/01/2024 | ASHIM SARKAR | 0.88 | 0.59 | 66.67 | 20
8 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15077 | Augmentation | continuation Work order for Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer Jalpaiguri R.W.S Sub-Division P.H.E. Dte. Jalpaiguri for 6 month (Period from 01.02.2024 to 31.07.2024) | Assistant Engineer | Junior Engineer | ORD/000793/2023-2024 | 93/RWS | 29/01/2024 | 27/07/2024 | ASHIM SARKAR | 0.88 | 0.81 | 91.81 | 50
9 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15077 | Augmentation | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of July 2024 |  |  | BILL/00519/2024-2025 | BP-2024-25-295 | 14/08/2024 |  | FILL & SMILE | 0.2 | 0 | 0 | null
10 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15077 | Augmentation | Supply mobil to vehicle no WB 71 A 5774 |  |  | BILL/00518/2024-2025 | BP-2024-25-296 | 14/08/2024 |  | FILL & SMILE | 0.02 | 0 | 0 | null
11 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15077 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF SONGACHI TG AREA PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000418/2023-2024 | 1332/NMD | 08/08/2023 | 07/09/2023 | ASHWIRBAD WOOD CRAFT | 12.01 | 5.68 | 47.27 | 90
Total | [13 empty] | 65.86 | 16.51 | 25.07