## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15077 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000095/2023-2024 | 1049/JD | 24/08/2023 | 24/08/2023 | Resource Division | 2.45 | 0 | 0 | 0
2 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15077 | Augmentation | New Service Connection Charge for SOONGACHI TEA GARDEN (REJU), T/W III, under MAL CCC, [APPLICATION NO. 4003220150, Reference ID : 403066255] |  |  | BILL/01071/2023-2024 | BP/23-24/107 | 30/09/2023 | 30/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15077 | Augmentation | Infrastructure Cost for SOONGACHI TEA GARDEN (REJU), T/W III, under MAL CCC, [APPLICATION NO. 100000088108, Reference ID : 860279669] |  |  | BILL/01072/2023-2024 | BP/23-24/107 | 30/09/2023 | 30/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.96 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15077 | Augmentation | FUEL BILL |  |  | BILL/00631/2023-2024 | BP-2023-24-433 | 11/10/2023 | 11/10/2023 | FILL & SMILE | 0.53 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15077 | Augmentation | Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer Jalpaiguri R.W.S Sub-Division P.H.E. Dte. Jalpaiguri for 6 month (Period from 01.08.2023 to 31.01.2024) |  |  | ORD/000268/2023-2024 | 877/RWS | 31/07/2023 | 31/01/2024 | ASHIM SARKAR | 0.88 | 0.88 | 100 | 20
6 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15077 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF SONGACHI TG AREA PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000418/2023-2024 | 1332/NMD | 08/08/2023 | 07/09/2023 | ASHWIRBAD WOOD CRAFT | 12.01 | 11.35 | 94.53 | 90
7 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15077 | Augmentation | continuation Work order for Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer Jalpaiguri R.W.S Sub-Division P.H.E. Dte. Jalpaiguri for 6 month (Period from 01.02.2024 to 31.07.2024) | Assistant Engineer | Junior Engineer | ORD/000793/2023-2024 | 93/RWS | 29/01/2024 | 29/07/2024 | ASHIM SARKAR | 0.88 | 0.88 | 100.14 | 50
8 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15077 | Augmentation | Construction of deep tube well by ODEX-195 method of drilling for Songachi T.G. Piped Water Supply Scheme, Block- Matiali, Dist- Jalpaiguri. | Assistant Engineer | Junior Engineer | ORD/000195/2022-2023 | 1592/JD | 17/08/2022 | 07/09/2022 | R.S CONSTRUCTION | 9.32 | 7.76 | 83.28 | 100
9 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15077 | Augmentation | Supply mobil to vehicle no WB 71 A 5774 |  |  | BILL/00518/2024-2025 | BP-2024-25-296 | 14/08/2024 | 14/08/2024 | FILL & SMILE | 0.02 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15077 | Augmentation | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of July 2024 |  |  | BILL/00519/2024-2025 | BP-2024-25-295 | 14/08/2024 | 14/08/2024 | FILL & SMILE | 0.2 | 0 | 0 | 0
11 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15077 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (MATIALI Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000993/2024-2025 | 13/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 36.03 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15077 | Augmentation | Sinking of 2 (Two) Nos Additional Tube Well by ODEX-165 method including Construction of different components i.e. Pump Houses, Boundary Walls, Rising Mains etc. for 4th and 5th site of Songachi Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000701/2024-2025 | 630/JD | 28/03/2025 | 27/05/2025 | PINAKI MITRA | 36.19 | 0 | 0 | 0
13 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15077 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
14 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15077 | Augmentation | Construction of different components of Rejuvenation of Songachi T.G. PWSS i.e pump houses, water distribution network, Boundary wall, Rising main, FHTC etc. in connection with JJM at Block - Matiali under jalpaiguri Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000088/2023-2024 | 441/JD. | 08/06/2023 | 31/03/2025 | PINAKI MITRA | 34.93 | 11.11 | 31.82 | 100
Total | [13 empty] | 685.67 | 31.99 | 4.67