## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme | SM/15078 | Augmentation | Emergency restoration work of pucca road that was damaged during pipe laying at Uttar Dangapara & Dakshin Sakoajhora Piped Water Supply Scheme in connection with JJM under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000022/2023-2024 | 122/JD | 28/04/2023 | 12/05/2023 | PARESH CHANDRA GUHA | 3.91 | 3.9 | 99.59 | 100
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme | SM/15078 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000097/2023-2024 | 1056/JD | 24/08/2023 | 24/08/2023 | Resource Division | 2.4 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme | SM/15078 | Augmentation | Construction of Pump House, Sinking Tube Well, Laying Rising Main etc of Uttar Dangapara & Dakshin Sakoajhora PWSS , in connection with Rejuvenation of Uttar Dangapara & Dakshin Sakoajhora PWSS under Jal Jeevan Mission at Banarhat Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000093/2023-2024 | 2000/JD | 19/05/2023 | 18/07/2023 | NARESH SEN | 19.29 | 9.08 | 47.08 | 15
4 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme | SM/15078 | Augmentation | Infrastructure development cost for new service connection at REJUVENATION OF UTTAR DANGAPARA AND DAKSHIN SAKOJHORA PWSS, TW no III GAIRKATA CCC APPLICATION NO. 100000111357 Reference ID : 860303377 |  |  | BILL/00590/2024-2025 | BP/24-25/143 | 01/08/2024 | 01/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.74 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme | SM/15078 | Augmentation | New Service Connection Charge for new service connection at REJUVENATION OF UTTAR DANGAPARA AND DAKSHIN SAKOJHORA PWSS, TW no III GAIRKATA CCC APPLICATION NO. 4003441947 Reference ID : 403241902 |  |  | BILL/00589/2024-2025 | BP/24-25/143 | 01/08/2024 | 01/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.82 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme | SM/15078 | Augmentation | Providing FHTC with LDS for direct boosting and Installation of Sluice Valve at different strategic point in connection with JJM of Uttar Dangapara and Dakshin Sakoajhora Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000533/2024-2025 | 124/JD | 16/01/2025 | 07/03/2025 | SUNIL ROY | 26.06 | 0 | 0 | 0
7 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme | SM/15078 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (BANARHAT Block ) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000987/2024-2025 | 11/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 57.53 | 0 | 0 | 0
8 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme | SM/15078 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: BANARHAT, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/001041/2024-2025 | 29/NMD | 06/01/2025 | 05/02/2025 | DIAMOND ELECTRICAL WORKS | 12.26 | 0 | 0 | 0
9 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme | SM/15078 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
Total | [13 empty] | 673.6 | 12.98 | 1.93