## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation for Manabari Tea Garden | SM/15082 | Augmentation | Construction of different components of Rejuvenation of Manabari Tea Garden PWSS i.e. TW, Pump Houses, Boundary Walls, Water Distribution Network, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000267/2023-2024 | 937/JD | 08/08/2023 | 31/08/2025 | TARAKESWAR PRASAD | 97.86 | 0 | 0 | 60
2 | JALPAIGURI |  | Northern Mechanical | Rejuvenation for Manabari Tea Garden | SM/15082 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF MANABARI TEA GARDEN PWSS, AT TW no III AND IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000426/2023-2024 | 1341/NMD | 08/08/2023 | 01/11/2026 | S.P. ENTERPRISE | 20.63 | 0 | 0 | 50
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation for Manabari Tea Garden | SM/15082 | Augmentation | Construction of G. I. line & concrete block & piller for culvert for Manabari Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000483/2022-2023 | 802/JD | 29/03/2023 | 19/04/2023 | M/S A.B.G. CONSTRUCTION | 3.02 | 2.98 | 98.76 | 100
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation for Manabari Tea Garden | SM/15082 | Augmentation | Construction of Approach Culvert with Guard Wall at H/W site for Manabari Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000381/2022-2023 | 359/JD | 20/02/2023 | 13/03/2023 | M/S A.B.G. CONSTRUCTION | 2.93 | 2.92 | 99.66 | 100
5 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation for Manabari Tea Garden | SM/15082 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000089/2023-2024 | 1064/JD | 24/08/2023 | 24/08/2023 | Resource Division | 19.68 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation for Manabari Tea Garden | SM/15082 | Augmentation | Sinking of 1 (One) No Big Dia (200mm x 150mm) Tube Well by Modified DTH - ODEX Method of drilling at Rejuvenation of Manabari Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000593/2023-2024 | 2332/JD | 08/02/2024 | 23/02/2024 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 16.63 | 14.02 | 84.27 | 100
7 | JALPAIGURI |  | Northern Mechanical | Rejuvenation for Manabari Tea Garden | SM/15082 | Augmentation | Infrastructure development cost for new service connection at REJU. OF MANABARI TG, TW NO-III, OODLABARI CCC APPLICATION NO. 100000118549 Reference ID : 860312789 |  |  | BILL/01398/2024-2025 | BP/24-25/237 | 25/10/2024 | 25/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.83 | 0 | 0 | 0
8 | JALPAIGURI |  | Northern Mechanical | Rejuvenation for Manabari Tea Garden | SM/15082 | Augmentation | New Service Connection Charge for REJU. OF MANABARI TG, TW NO-III, OODLABARI CCC APPLICATION NO. 4003491167 Reference ID : 403275173 |  |  | BILL/01399/2024-2025 | BP/24-25/237 | 25/10/2024 | 25/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
9 | JALPAIGURI |  | Northern Mechanical | Rejuvenation for Manabari Tea Garden | SM/15082 | Augmentation | Installation of two tank chlorination system at different water supply scheme of JJM under Mal Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001002/2024-2025 | 55/HQ/NMD | 06/01/2025 | 13/01/2025 | SARKAR ELECTRIC | 0.95 | 0 | 0 | 0
10 | JALPAIGURI |  | Northern Mechanical | Rejuvenation for Manabari Tea Garden | SM/15082 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAL, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001005/2024-2025 | 25/NMD | 06/01/2025 | 05/02/2025 | CHOWDHURY AND BASU ENTERPRISE | 15.33 | 0 | 0 | 0
11 | JALPAIGURI |  | Northern Mechanical | Rejuvenation for Manabari Tea Garden | SM/15082 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
Total | [13 empty] | 316.9 | 19.92 | 6.29