## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation for Patkidaha Piped Water Supply Scheme | SM/15085 | Augmentation | Retrofitting of distribution pipeline network within Patkidaha Mouza (Phase-I) of Patkidaha Water Supply Scheme at Dhupguri Development Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000493/2021-2022 | 1936/JD | 29/11/2021 | 14/12/2021 | PRABIR SHOME | 3.75 | 3.63 | 96.83 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation for Patkidaha Piped Water Supply Scheme | SM/15085 | Augmentation | Retrofitting of distribution pipeline network within Dambari Mouza (Phase-I) of Patkidaha Water Supply Scheme at Dhupguri Development Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000492/2021-2022 | 1935/JD | 29/11/2021 | 14/12/2021 | KULDIP KAPOOR | 1.47 | 0 | 0 | 100
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation for Patkidaha Piped Water Supply Scheme | SM/15085 | Augmentation | Retrofitting of distribution pipeline network within Patkidaha Mouza (Phase-II) of Patkidaha Water Supply Scheme at Dhupguri Development Block under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000223/2022-2023 | 1852/JD | 16/09/2022 | 07/10/2022 | SADHAN KARMAKAR | 2.8 | 2.58 | 92.38 | 1
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation for Patkidaha Piped Water Supply Scheme | SM/15085 | Augmentation | Restoration of damaged DI pipeline at Patkidaha Piped W/S Scheme at Dhupguri Development Block under Jalpaiguri Division P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000100/2022-2023 | 1312/JD | 15/06/2022 | 30/06/2022 | M/S SIBU DEY AND CO. | 1.82 | 1.24 | 68.15 | 100
5 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation for Patkidaha Piped Water Supply Scheme | SM/15085 | Augmentation | Retrofitting of distribution pipeline network within Dakhsin Dangapara Mouza (Phase-II) of Patkidaha Water Supply Scheme at Dhupguri Development Block under Jalpaiguri Division P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000047/2022-2023 | 940/JD | 18/04/2022 | 03/05/2022 | SUKES BASU MAJUMDAR | 1.25 | 1.25 | 99.72 | 100
6 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation for Patkidaha Piped Water Supply Scheme | SM/15085 | Augmentation | Construction of Pump House, Sinking Tube Well, Laying Rising Main etc of Patkidaha PWSS , in connection with Rejuvenation of Patkidaha PWSS under Jal Jeevan Mission at Dhupguri Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,Assistant Engineer,HQ | Junior Engineer | ORD/000104/2023-2024 | 374/JD | 30/05/2023 | 26/03/2025 | SADHAN KARMAKAR | 47.23 | 36.48 | 77.24 | 20
7 | JALPAIGURI |  | Northern Mechanical | Rejuvenation for Patkidaha Piped Water Supply Scheme | SM/15085 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF PATKIDAHA PWSS, TW NO- III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD,Driller-in-Charge | Junior Engineer | ORD/000026/2023-2024 | 476/NMD | 26/04/2023 | 26/05/2023 | BONANZA ENTERPRISE | 11.5 | 11.49 | 99.92 | 100
8 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation for Patkidaha Piped Water Supply Scheme | SM/15085 | Augmentation | Retrofittings of distribution pipeline network within Dambari Mouza (Phase-II) of Patkidaha Water Supply Scheme at Dhupguri development Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000527/2023-2024 | 1786/JD | 08/12/2023 | 29/12/2023 | KULDIP KAPOOR | 4.3 | 4.03 | 93.86 | 100
9 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation for Patkidaha Piped Water Supply Scheme | SM/15085 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000090/2023-2024 | 1062/JD | 24/08/2023 | 24/08/2023 | Resource Division | 2.4 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation for Patkidaha Piped Water Supply Scheme | SM/15085 | Augmentation | Construction of Boundary Wall, Pathway, Drain, Providing FHTC, IEP Washout etc. at 3rd TW Site for Patkidaha PWSS icw JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000140/2024-2025 | 1529/JD | 01/10/2024 | 01/07/2025 | SADHAN KARMAKAR | 15.77 | 0 | 0 | 40
11 | JALPAIGURI |  | Northern Mechanical | Rejuvenation for Patkidaha Piped Water Supply Scheme | SM/15085 | Augmentation | New Service Connection Charge for REJU PATKIDHAHA, T/W No. III, under DHUPGURI CCC [APPLICATION NO. 4003328075 , Reference ID : 403153542] |  |  | BILL/01997/2023-2024 | BP/23-24/308 | 09/02/2024 | 09/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.63 | 0 | 0 | 0
12 | JALPAIGURI |  | Northern Mechanical | Rejuvenation for Patkidaha Piped Water Supply Scheme | SM/15085 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
13 | JALPAIGURI |  | Northern Mechanical | Rejuvenation for Patkidaha Piped Water Supply Scheme | SM/15085 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
Total | [13 empty] | 729.81 | 60.71 | 8.32