## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF AMBARI FALAKATA PIPED WATER SUPPLY SCHEME | SM/15089 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Ambari Falakata P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000578/2021-2022 | 158/JD | 19/01/2022 | 20/03/2022 | MAA ENTERPRISES | 4.65 | 0 | 0 | 100
2 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF AMBARI FALAKATA PIPED WATER SUPPLY SCHEME | SM/15089 | Augmentation | Construction of different components of Rejuvenation of Ambari Falakata PWSS ie. TW, Pump Houses, Water distribution Network, IEP etc. in connection with Jal Jeevan Mission at Rajganj Block, under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000074/2023-2024 | 429/JD. | 08/06/2023 | 01/04/2025 | KANAI LAL SEN | 82.62 | 9.86 | 11.94 | 85
3 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF AMBARI FALAKATA PIPED WATER SUPPLY SCHEME | SM/15089 | Augmentation | Overhauling and Reconditioning of The IEP (2 Unit) other Ancillary Works at Ambari Falakata H/W Site at Block Rajganj, under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000133/2024-2025 | 1292/JD | 04/09/2024 | 04/10/2024 | BAJRANG ENTERPRISE | 12.02 | 11.56 | 96.2 | 100
4 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF AMBARI FALAKATA PIPED WATER SUPPLY SCHEME | SM/15089 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF AMBARI FALAKATA PWSS,at TW NO V in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000202/2024-2025 | 1378/NMD | 13/08/2024 | 01/05/2025 | R.K.ENTERPRISES | 12.13 | 2.85 | 23.5 | 100
5 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF AMBARI FALAKATA PIPED WATER SUPPLY SCHEME | SM/15089 | Augmentation | New Service Connection Charge for AMBARI FALAKATA, T/WNO. V under FULBARIHAT CCC APPLICATION NO. 4003385989 Reference ID : 403199279 |  |  | BILL/00182/2024-2025 | BP/24-25/25 | 09/05/2024 | 09/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.12 | 0 | 0 | 0
Total | [13 empty] | 120.54 | 24.27 | 20.14