## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF BHANDANI PIPED WATER SUPPLY SCHEME | SM/15094 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000099/2023-2024 | 1054/JD | 24/08/2023 | 24/08/2023 | Resource Division | 1.25 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF BHANDANI PIPED WATER SUPPLY SCHEME | SM/15094 | Augmentation | Providing FHTC Including Restoration of Existing FHTC in the Command Area of Bhandani PWSS in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000505/2024-2025 | 2398/JD | 19/12/2024 | 18/01/2025 | SANJIT SAHA | 6.96 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF BHANDANI PIPED WATER SUPPLY SCHEME | SM/15094 | Augmentation | Laying distribution system along with ancillary works for Rejuvenation of Bhandani Piped water supply scheme in connection with Jal Jeevan mission at Dhupguri Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000009/2024-2025 | 422/JD | 12/06/2024 | 01/05/2025 | SANJIT SAHA | 29.06 | 0 | 0 | 50
4 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF BHANDANI PIPED WATER SUPPLY SCHEME | SM/15094 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF BHANDANI PIPED WATER SUPPLY SCHEME | SM/15094 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/001049/2024-2025 | 31/NMD | 06/01/2025 | 05/02/2025 | ANIMA ENTERPRISE | 15.32 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF BHANDANI PIPED WATER SUPPLY SCHEME | SM/15094 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF BHANDANI PIPED WATER SUPPLY SCHEME | SM/15094 | Augmentation | Construction of Pump House, Sinking Tube Well, Laying Rising Main etc of Bhandani PWSS , in connection with Rejuvenation of Bhandani PWSS under Jal Jeevan Mission at Dhupguri Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000143/2023-2024 | 703/JD | 13/07/2023 | 01/04/2025 | GOURAB GUHA ROY | 36.18 | 0 | 0 | 55
8 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF BHANDANI PIPED WATER SUPPLY SCHEME | SM/15094 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF BHANDANI PWSS, TW NO- III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD,Driller-in-Charge | Junior Engineer | ORD/000062/2023-2024 | 594/NMD | 18/05/2023 | 01/09/2025 | M/S ROYAL ENTERPRISE | 11.45 | 0 | 0 | 100
Total | [13 empty] | 734.11 | 0 | 0