## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mathachulka Piped Water Supply Scheme | SM/15098 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000086/2023-2024 | 1067/JD | 24/08/2023 | 24/08/2023 | Resource Division | 17.44 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mathachulka Piped Water Supply Scheme | SM/15098 | Augmentation | Repairing of Pump House ( 1st site ), boundary wall ( 1st site ) and other Allied works at MATHACHULKA Piped Water Supply Scheme under Jalpaiguri Division ,P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000115/2022-2023 | 92/JSSD | 22/07/2022 | 06/08/2022 | DEBABRATA SARKAR | 4.62 | 0 | 0 | 100
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mathachulka Piped Water Supply Scheme | SM/15098 | Augmentation | Construction of different components of Rejuvenation of Mathachulka PWSS i.e. TW, Pump Houses, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Metali under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000141/2023-2024 | 701/JD | 13/07/2023 | 02/01/2025 | M/S. D.K. DEY & CO.. | 77.02 | 0 | 0 | 85
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mathachulka Piped Water Supply Scheme | SM/15098 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000209/2023-2024 | 2069/JD | 10/01/2024 | 10/01/2024 | Resource Division | 4 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mathachulka Piped Water Supply Scheme | SM/15098 | Augmentation | "New Service Connection Charge fo MATHACHULKA PWSS TW NO-III, METELI CCC " APPLICATION NO.4003386724 Reference ID : 403200293 |  |  | BILL/00389/2024-2025 | BP/24-25/73 | 30/05/2024 | 30/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mathachulka Piped Water Supply Scheme | SM/15098 | Augmentation | "INFRA COST IRO NSC POLECASE for MATHACHULKA TW-IV(NEW MASJID),METELI CCC " Reference No-860314555 Application No-100000120355 |  |  | BILL/01393/2024-2025 | BP/24-25/237 | 25/10/2024 | 25/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.34 | 0 | 0 | 0
7 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mathachulka Piped Water Supply Scheme | SM/15098 | Augmentation | "New Service Connection Charge for MATHACHULKA TW-IV(NEW MASJID),METELI CCC Reference ID:403285589 Application Id:4003505421 |  |  | BILL/01392/2024-2025 | BP/24-25/237 | 25/10/2024 | 25/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
8 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mathachulka Piped Water Supply Scheme | SM/15098 | Augmentation | "INFRA COST IRO NSC for (REJU) MATHACHULKA TG PWSS TW NO-III, METELI CCC " APPLICATION NO.100000105524 Reference ID : 860297574 |  |  | BILL/00246/2024-2025 | BP/24-25/25 | 09/05/2024 | 09/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.59 | 0 | 0 | 0
9 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mathachulka Piped Water Supply Scheme | SM/15098 | Augmentation | Installation of two tank chlorination system at REJUVENATION OF METELI BAZAR PWSS(TW-I) and other adjacent water supply scheme UNDER JJM under METELI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000095/2025-2026 | 1085/HQ/NMD | 15/05/2025 | 22/05/2025 | D.K. & SONS | 0.63 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mathachulka Piped Water Supply Scheme | SM/15098 | Augmentation | Balance work in connection with Laying Distribution System at Mathachulka Piped Water Supply Scheme in connection with Jal Jeevan Mission at Matiali Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000180/2025-2026 | 2166/JD | 30/10/2025 | 29/11/2025 | DEEP CONSTRUCTION | 24.8 | 0 | 0 | 0
11 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Mathachulka Piped Water Supply Scheme | SM/15098 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF MATHACHULKA PWSS, TW no III,IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000172/2023-2024 | 1214/NMD | 26/07/2023 | 31/07/2025 | MUSTAFI CONCERN | 22.13 | 0 | 0 | 100
Total | [13 empty] | 159.94 | 0 | 0