## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Palasbari Tea Garden Area Piped Water Supply Scheme | SM/15099 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF PALASBARI TEA GARDEN AREA PWSS, TW NO III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000667/2023-2024 | 1482/NMD | 17/08/2023 | 16/09/2023 | SUDIP DUTTA | 10.76 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Palasbari Tea Garden Area Piped Water Supply Scheme | SM/15099 | Augmentation | Construction of Boundary Wall Surface, Drain, Pathway with related ancillary work at Head Works site of Palashbari Tea Garden Area PWSS under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000783/2021-2022 | 839/JD | 31/03/2022 | 30/04/2022 | DULAL CHOUDHURY | 28.53 | 13.25 | 46.45 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Palasbari Tea Garden Area Piped Water Supply Scheme | SM/15099 | Augmentation | Construction of different components of Rejuvenation Of Palashbari Tea Garden PWSS i.e. TW, Pump Houses, Water distribution Network, RISING MAIN etc. in connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000082/2023-2024 | 435/JD. | 08/06/2023 | 14/08/2025 | LOKNATH CONSTRUCTION | 77.09 | 21.8 | 28.28 | 41
4 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Palasbari Tea Garden Area Piped Water Supply Scheme | SM/15099 | Augmentation | New Service Connection Charge for REJU PALASHBARI, T/W No. III, under BANARHAT CCC [APPLICATION NO. 400333017 , Reference ID : 403157467] |  |  | BILL/02000/2023-2024 | BP/23-24/308 | 09/02/2024 | 09/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.9 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Palasbari Tea Garden Area Piped Water Supply Scheme | SM/15099 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (BANARHAT Block ) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000987/2024-2025 | 11/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 57.53 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Palasbari Tea Garden Area Piped Water Supply Scheme | SM/15099 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
Total | [13 empty] | 725.41 | 35.05 | 4.83