## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF PORA PARA PWSS | SM/15101 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF PORAPARA PWSS, TW NO I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000236/2023-2024 | 1251/NMD | 31/07/2023 | 30/08/2023 | TAPAN BISWAS | 10.86 | 10.83 | 99.77 | 100
2 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF PORA PARA PWSS | SM/15101 | Augmentation | Construction of different components for Rejuvenation of Porapara PWSS I.e. TW, Pump Houses, Boundary wall IEP, Rising main etc. at Block - Jalpaiguri Sadar under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000075/2023-2024 | 1003/JD | 17/05/2023 | 01/07/2023 | B.M CONSTRUCTION | 51.2 | 51.2 | 100 | 100
3 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF PORA PARA PWSS | SM/15101 | Augmentation | Emergency extension and reparing of pipe line to facilite FHTC at different location Pora Para Water Supply Scheme under Jalpaiguri Division, PHE Dte. Under JJM. | Assistant Engineer | Junior Engineer | ORD/000448/2023-2024 | 1282/RWS | 28/11/2023 | 18/12/2023 | B.M CONSTRUCTION | 6.16 | 6.12 | 99.37 | 100
4 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF PORA PARA PWSS | SM/15101 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF PORAPARA PWSS, TW no V in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000327/2023-2024 | 1298/NMD | 03/08/2023 | 02/09/2023 | M/S ANJALI ENTERPRISE | 12.62 | 12.62 | 100 | 100
5 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF PORA PARA PWSS | SM/15101 | Augmentation | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Sadar block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. | Assistant Engineer | Junior Engineer | ORD/000457/2023-2024 | 1290/RWS | 29/11/2023 | 29/12/2023 | B.M CONSTRUCTION | 3.89 | 3.89 | 100 | 100
6 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF PORA PARA PWSS | SM/15101 | Augmentation | Sinking of one No. tube well (250mm x 200mm) by Reverse Rotary Method of Drilling and Construction of Pump House (5.40m x 3.60m) and Iron Elimination Plant for direct boosting arrangement for Augmentation of Porapara Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000069/2024-2025 | 988/JD | 14/08/2024 | 12/12/2024 | SADHAN KARMAKAR | 38.03 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF PORA PARA PWSS | SM/15101 | Augmentation | Construction of different balance components of Rejuvenation of Porapara PWSS in connection with Jal Jeevan Mission at Block - Jalpaiguri Sadar under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000728/2023-2024 | 2494/JD | 28/02/2024 | 01/05/2025 | SUKES BASU MAJUMDAR | 74.69 | 0 | 0 | 100
8 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF PORA PARA PWSS | SM/15101 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000077/2024-2025 | 2208/JD | 01/12/2024 | 01/12/2024 | Resource Division | 24.23 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF PORA PARA PWSS | SM/15101 | Augmentation | Supply of Different Stationary Items for Office Use under Jalpaiguri RWS Sub Division. PHE Dte. |  |  | BILL/00927/2024-2025 | BP-2024-25-515 | 14/11/2024 | 14/11/2024 | JALPAIGURI WHOLESALE CONSUMER'S CO-OPERATIVE SOCIETY LTD. | 0.23 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF PORA PARA PWSS | SM/15101 | Augmentation | Supplying and Installation of Display Boards at different piped water supply schemes in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000100/2025-2026 | 479/RWS | 29/05/2025 | 28/06/2025 | JAYDEB SAHA | 7.95 | 0 | 0 | 100
11 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF PORA PARA PWSS | SM/15101 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
Total | [13 empty] | 777.45 | 84.67 | 10.89