## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvanation of Riabari Tea Garden Area Piped Water Supply Scheme | SM/15103 | Augmentation | Relaying of Rising Main from Head Works Site to Pump House No.-II due to the Damage of HDPE Pipeline at Riabari T.G PWSS under Jalpaiguri Division, P.H.E. |  |  | ORD/000507/2024-2025 | 2403/JD | 20/12/2024 | 09/01/2025 | SAPTASWA SARKAR | 1.32 | 0 | 0 | 0
2 | JALPAIGURI |  | Northern Mechanical | Rejuvanation of Riabari Tea Garden Area Piped Water Supply Scheme | SM/15103 | Augmentation | New Service Connection Charge for REJU RIA BARI TEA GARDEN, T/W No. III, under BANARHAT CCC [APPLICATION NO. 4003333061 , Reference ID : 403157468] |  |  | BILL/02006/2023-2024 | BP/23-24/308 | 09/02/2024 | 09/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 15.73 | 0 | 0 | 0
3 | JALPAIGURI |  | Northern Mechanical | Rejuvanation of Riabari Tea Garden Area Piped Water Supply Scheme | SM/15103 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (BANARHAT Block ) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000987/2024-2025 | 11/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 57.53 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | Rejuvanation of Riabari Tea Garden Area Piped Water Supply Scheme | SM/15103 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
Total | [13 empty] | 622.16 | 0 | 0