## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF JABRAMALI PIPED WATER SUPPLY SCHEME | SM/15109 | Augmentation | Retrofitting works & other ancillary works related to FHTC at different places of Jabramali PWSS under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000433/2022-2023 | 629/JD | 13/03/2023 | 12/04/2023 | DREAM CONSTRUCTION | 12.41 | 12.39 | 99.87 | 100
2 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF JABRAMALI PIPED WATER SUPPLY SCHEME | SM/15109 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000094/2023-2024 | 1050/JD | 24/08/2023 | 24/08/2023 | Resource Division | 4.8 | 0 | 0 | 0
3 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF JABRAMALI PIPED WATER SUPPLY SCHEME | SM/15109 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF JABRAMALI PWSS, TW NO-III,IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000173/2023-2024 | 1215/NMD | 26/07/2023 | 25/08/2023 | SUNLIT | 22.15 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF JABRAMALI PIPED WATER SUPPLY SCHEME | SM/15109 | Augmentation | Drainage line for IEP & other ancillary works at Head work site of JABRAMALI PWSS under Jalpaiguri Divisiopn PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000447/2023-2024 | 1281/RWS | 28/11/2023 | 18/12/2023 | RAGHU DAS | 3.04 | 2.96 | 97.5 | 100
5 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF JABRAMALI PIPED WATER SUPPLY SCHEME | SM/15109 | Augmentation | Supply and Delivery of C.I special as when as required at T/W No-I of JABRAMALI and other adjacent W/S Scheme under in the Dist. of JALPAIGURI. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000066/2024-2025 | 1055/HQ/NMD | 21/06/2024 | 28/06/2024 | B.B. CONCERNED | 0.73 | 0 | 0 | 100
6 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF JABRAMALI PIPED WATER SUPPLY SCHEME | SM/15109 | Augmentation | New Service Connection Charge for JABRAMALI(REJU), T/W-IV under MAYNAGURI CCC APPLICATION NO. 4003397114 Reference ID : 403208952 |  |  | BILL/00281/2024-2025 | BP/24-25/36 | 14/05/2024 | 14/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.69 | 0 | 0 | 0
7 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF JABRAMALI PIPED WATER SUPPLY SCHEME | SM/15109 | Augmentation | New Service Connection Charge for JABRAMALI(REJU), T/W-III under MAYNAGURI CCC APPLICATION NO. 4003397105 Reference ID : 403208949 |  |  | BILL/00282/2024-2025 | BP/24-25/36 | 14/05/2024 | 14/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF JABRAMALI PIPED WATER SUPPLY SCHEME | SM/15109 | Augmentation | Construction of different components of Rejuvenation of Jabramali PWSS i.e. TW, Pump Houses, Water distribution Network, Boundary wall, RISING MAIN etc. in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000361/2023-2024 | 1435/JD | 05/10/2023 | 02/04/2026 | RAGHU DAS | 83.33 | 17.58 | 21.09 | 80
Total | [13 empty] | 137.15 | 32.93 | 24.01