## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme | SM/15114 | Augmentation | Retroffitting works, repairing of 2 nos pump house 2 nos boundary wall, repairing of Rising main line and other allied works at Chilaoni TG Area Piped water supply Scheme under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000398/2022-2023 | 607/JD | 09/03/2023 | 08/04/2023 | SUJAN LAMA | 29.35 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme | SM/15114 | Augmentation | Sinking of 2 Nos. 183 mm x 125mm dia 120 m Deep tube well by ODEX-165 method of drilling at Chilaoni TG area Piped Water Supply Scheme under PHE Dte. Jalpaiguri Division. | Assistant Engineer | Junior Engineer | ORD/000075/2022-2023 | 1314/JD | 16/06/2022 | 16/07/2022 | S. N. POLYMERS PVT. LTD. | 13.84 | 0 | 0 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme | SM/15114 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000082/2023-2024 | 1069/JD | 24/08/2023 | 24/08/2023 | Resource Division | 15.45 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme | SM/15114 | Augmentation | Infrastructure Cost for CHALOUNI T.G RANA LINE W/S Scheme, T/W No. IV, under METELLI CCC, [APPLICATION NO. 100000066825, Reference ID : 860257225] |  |  | BILL/00705/2022-2023 | BP/22-23/144 | 04/03/2023 | 04/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.29 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme | SM/15114 | Augmentation | New Service Connection Charge for CHALOUNI T.G NEW LINE W/S Scheme, T/W No. IV, under METELLI CCC, [APPLICATION NO. 4002964337, Reference ID : 402851946] |  |  | BILL/00702/2022-2023 | BP/22-23/144 | 04/03/2023 | 04/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme | SM/15114 | Augmentation | Infrastructure Cost for CHALOUNI T.G NEW LINE W/S Scheme, T/W No. IV, under METELLI CCC W/S Scheme, , [APPLICATION NO. 100000066826, Reference ID : 860257226] |  |  | BILL/00703/2022-2023 | BP/22-23/144 | 04/03/2023 | 04/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.13 | 0 | 0 | 0
7 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme | SM/15114 | Augmentation | New Service Connection Charge for CHALOUNI T.G RANA LINE W/S Scheme, T/W No. IV, under METELLI CCC, [APPLICATION NO. 4002964336, Reference ID : 402851948] |  |  | BILL/00704/2022-2023 | BP/22-23/144 | 04/03/2023 | 04/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme | SM/15114 | Augmentation | Construction of Pump House (3.60 x2.40) size with sanitary & plumbing arrangement at 3rd tube well site for Chilouni TG P.W.S.S. under Jalpaiguri Division,P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000087/2022-2023 | 74/JSSD | 22/07/2022 | 05/09/2022 | SUJAN LAMA | 4.65 | 4.65 | 100 | 100
9 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme | SM/15114 | Augmentation | Construction of Pump House (3.60 x2.40) size with sanitary & plumbing arrangement at 4th tube well site for Chilouni TG P.W.S.S. under Jalpaiguri Division,P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000123/2022-2023 | 75/JSSD | 22/07/2022 | 05/09/2022 | SUJOY CHOWDHURY | 4.65 | 4.65 | 100 | 100
10 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme | SM/15114 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF CHILOUNI TG AREA PWSS, TW no III,IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000029/2023-2024 | 477/NMD | 26/04/2023 | 26/05/2023 | SUNRISE ENGINEERING CORPORATION | 22.76 | 22.74 | 99.93 | 100
11 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme | SM/15114 | Augmentation | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Matiali block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. | Assistant Engineer | Junior Engineer | ORD/000454/2023-2024 | 1286/RWS | 28/11/2023 | 28/12/2023 | B.M CONSTRUCTION | 3.11 | 3.11 | 100 | 100
12 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme | SM/15114 | Augmentation | Installation of two tank chlorination system at REJUVENATION OF METELI BAZAR PWSS(TW-I) and other adjacent water supply scheme UNDER JJM under METELI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000095/2025-2026 | 1085/HQ/NMD | 15/05/2025 | 22/05/2025 | D.K. & SONS | 0.63 | 0 | 0 | 0
Total | [13 empty] | 103.23 | 35.16 | 34.06