## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Syli Tea Garden Area Piped Water Supply Scheme | SM/15117 | Augmentation | Emergent repairing of Over Head Reservior(OHR) at Syli Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000382/2022-2023 | 346/JD | 16/02/2023 | 18/03/2023 | RAGHU DAS | 4.12 | 0 | 0 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Syli Tea Garden Area Piped Water Supply Scheme | SM/15117 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000059/2023-2024 | 1094/JD | 24/08/2023 | 24/08/2023 | Resource Division | 9.89 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Syli Tea Garden Area Piped Water Supply Scheme | SM/15117 | Augmentation | Sinking of 2 Nos. Big dia Tube well 250x200mm dia using MS Slotted strainer at required depth by Reverse Rotary method of drilling i.c.w Rejuvenation of Syli Tea Garden Water Supply Scheme under Jal Jeevan Mission, Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000296/2023-2024 | 1354/JD | 26/09/2023 | 26/10/2023 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 40.77 | 0 | 0 | 60
4 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Syli Tea Garden Area Piped Water Supply Scheme | SM/15117 | Augmentation | Supply and Delivery of C.I special for as when as required at T/W No-I of SYLI TG and other adjacent W/S Scheme under in the Dist. of JALPAIGURI. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000069/2024-2025 | 1058/HQ/NMD | 21/06/2024 | 28/06/2024 | BONANZA ENTERPRISE | 0.73 | 0 | 0 | 100
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Syli Tea Garden Area Piped Water Supply Scheme | SM/15117 | Augmentation | New Service Connection Charge for REJU. OF SYLI TG, TW NO-IV, OODLABARI CCC APPLICATION NO. 4003343252 Reference ID : 403165542 |  |  | BILL/00191/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Syli Tea Garden Area Piped Water Supply Scheme | SM/15117 | Augmentation | New Service Connection Charge for REJU. OF SYLI TG, TW NO-III, OODLABARI CCC APPLICATION NO. 4003343254 Reference ID : 403165543 |  |  | BILL/00189/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
7 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Syli Tea Garden Area Piped Water Supply Scheme | SM/15117 | Augmentation | Infrastructure development cost for new service connection at REJU. OF SYLI TG, TW NO-IV, OODLABARI CCC APPLICATION NO. 100000101047 Reference ID : 860293437 |  |  | BILL/00192/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.81 | 0 | 0 | 0
8 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Syli Tea Garden Area Piped Water Supply Scheme | SM/15117 | Augmentation | Infrastructure development cost for new service connection at REJU. OF SYLI TG, TW NO-III, OODLABARI CCC APPLICATION NO. 100000101048 Reference ID : 860293438 |  |  | BILL/00190/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.89 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Syli Tea Garden Area Piped Water Supply Scheme | SM/15117 | Augmentation | Construction of different components of Rejuvenation of Syli Tea Garden PWSS i.e TW, Pump Houses, Boundary Walls, Water Distribution Network(convertion), Rising Main etc in connection with Jal Jeevan Mission at Block- Mal under Jalpaiguri Division,P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000034/2023-2024 | 128/JD | 28/04/2023 | 10/02/2025 | SAHA CONSTRUCTION | 104.75 | 0 | 0 | 90
10 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Syli Tea Garden Area Piped Water Supply Scheme | SM/15117 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF SYLI TG PWSS, TW no III & IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000675/2023-2024 | 1489/NMD | 17/08/2023 | 16/09/2023 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 23.84 | 0 | 0 | 80
Total | [13 empty] | 193.17 | 0 | 0