## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | RETROFITTING OF MAHITNAGAR PWSS | SM/15131 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at balance portion of Mohitnagar W/S Scheme in connection with Jaldhara/ Jal Sapna under Jalpaiguri Division PHE Dte. (PART-J) | Assistant Engineer | Junior Engineer | ORD/000259/2023-2024 | 1269/JD | 13/09/2023 | 13/10/2023 | M/S DEY & ROY CHOUDHURY | 63.37 | 0 | 0 | 90
2 | JALPAIGURI |  | Jalpaiguri Division | RETROFITTING OF MAHITNAGAR PWSS | SM/15131 | Retrofitting | Retrofitting by replacement of lower (63 mm ,75mm) dia UPVC pipe of Mahit Nagar PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000080/2023-2024 | 433/JD. | 08/06/2023 | 06/07/2023 | RAGHU DAS | 52.95 | 0 | 0 | 98
Total | [13 empty] | 116.32 | 0 | 0