## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | RETROFITTING OF ARJI MARIA KAMALA PUKHARI PIPED WATER SUPPLY SCHEME | SM/15132 | Retrofitting | Retrofitting by replacement of lower (63 mm ,75mm) dia UPVC pipe of Arji Maria Kamala Pukhari PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000079/2023-2024 | 432/JD. | 08/06/2023 | 06/07/2023 | GOUTAM DAS | 55.33 | 0 | 0 | 100
2 | JALPAIGURI |  | Jalpaiguri Division | RETROFITTING OF ARJI MARIA KAMALA PUKHARI PIPED WATER SUPPLY SCHEME | SM/15132 | Retrofitting | Installation of 2 Nos of Iron Elimination Plant (20m3/hr.) including construction of 2 nos of Blower room (3.60MX3.00M) Size & concrete platform , drain, valve chamber etc at 3rd and 4th Site of Arji maria kamala pukhari piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000560/2023-2024 | 2175/JD | 22/01/2024 | 22/03/2024 | R.S CONSTRUCTION | 28.19 | 0 | 0 | 100
3 | JALPAIGURI |  | Jalpaiguri Division | RETROFITTING OF ARJI MARIA KAMALA PUKHARI PIPED WATER SUPPLY SCHEME | SM/15132 | Retrofitting | Laying Washout line at 4th Site and Replacement of damaged higher dia pipeline at Arjimaria Kamalapukuri Piped Water Supply Scheme in connection with Jal Jeevan Mission at Block - Jalpaiguri Sadar under Jalpaiguri District, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000187/2025-2026 | 2169/JD | 30/10/2025 | 01/04/2026 | SOUVIK SAHA | 14 | 0 | 0 | 100
Total | [13 empty] | 97.51 | 0 | 0