## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Northern Mechanical | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/15261 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DIANA TG(D) PWSS, TW NO- I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000886/2022-2023 | 369/NMD | 29/03/2023 | 28/04/2023 | THE BANERJEE CONCERN | 24.35 | 0 | 0 | 0
2 | JALPAIGURI | Dhupguri | Jalpaiguri Division | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/15261 | New | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 150/JD | 28/04/2023 | 28/04/2023 | Resource Division | 15.68 | 0 | 0 | 0
3 | JALPAIGURI | Dhupguri | Jalpaiguri Division | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/15261 | New | Material Requisition To Resource Division |  |  | RTOR000119/2023-2024 | 1830/JD | 15/12/2023 | 15/12/2023 | Resource Division | 5.95 | 0 | 0 | 0
4 | JALPAIGURI | Dhupguri | Northern Mechanical | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/15261 | New | Infrastructure Cost for DIANA TEA GAEDEN, T/W I, under BANARHAT CCC [APPLICATION NO. 100000083813 ; Reference ID : 860275313] |  |  | BILL/00996/2023-2024 | BP/23-24/99 | 12/09/2023 | 12/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.15 | 0 | 0 | 0
5 | JALPAIGURI | Dhupguri | Northern Mechanical | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/15261 | New | New Service Connection Charge for DIANA TEA GAEDEN, T/W I, under BANARHAT CCC [APPLICATION NO. 4003193588 ; Reference ID : 403045950] |  |  | BILL/00995/2023-2024 | BP/23-24/99 | 12/09/2023 | 12/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
6 | JALPAIGURI | Dhupguri | Northern Mechanical | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/15261 | New | Infrastructure Cost for DIANA TEA GAEDEN, T/W II, under BANARHAT CCC [APPLICATION NO. 100000083815 ; Reference ID : 860275315] |  |  | BILL/01008/2023-2024 | BP/23-24/99 | 12/09/2023 | 12/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.32 | 0 | 0 | 0
7 | JALPAIGURI | Dhupguri | Northern Mechanical | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/15261 | New | New Service Connection Charge for DIANA TEA GAEDEN, T/W II, under BANARHAT CCC [APPLICATION NO. 4003193593 ; Reference ID : 403045952] |  |  | BILL/01007/2023-2024 | BP/23-24/99 | 12/09/2023 | 12/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
8 | JALPAIGURI | Dhupguri | Jalpaiguri Division | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/15261 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
9 | JALPAIGURI | Dhupguri | Jalpaiguri Division | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/15261 | New | Construction of Boundary Wall, Drain, Footpath including Balance Portion of Distribution Network and other Allied Works related to Pipe Line at Diana Tea Garden Piped Water Supply Scheme in connection with Jal Jeevan Mission at Banarhat Block under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000362/2024-2025 | 2012/JD | 18/11/2024 | 18/12/2024 | VISHAL ENTERPRISES | 9.7 | 0 | 0 | 0
10 | JALPAIGURI | Dhupguri | Northern Mechanical | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/15261 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: BANARHAT, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/001045/2024-2025 | 30/NMD | 06/01/2025 | 05/02/2025 | GEETA CONSTRUCTION | 12.33 | 0 | 0 | 0
11 | JALPAIGURI | Dhupguri | Northern Mechanical | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/15261 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (BANARHAT Block ) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000987/2024-2025 | 11/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 57.53 | 0 | 0 | 0
12 | JALPAIGURI | Dhupguri | Northern Mechanical | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/15261 | New | Installation of two tank chlorination system at different water supply scheme UNDER JJM under BANARHAT Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Driller-in-Charge |  | ORD/001136/2024-2025 | 52/DSD | 10/03/2025 | 25/03/2025 | D.K. & SONS | 1.39 | 0 | 0 | 0
13 | JALPAIGURI | Dhupguri | Jalpaiguri Division | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/15261 | New | Continuation order for the work of supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi Permit). (Vehicle No. WB71B-8742) (From 01.04.2025 to 30.04.2025) | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000787/2024-2025 | 108-HQ/JD | 28/03/2025 | 28/04/2025 | RAKESH SARKAR | 0.15 | 0.15 | 100 | 0
14 | JALPAIGURI | Dhupguri | Northern Mechanical | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/15261 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
Total | [13 empty] | 714.14 | 0.15 | 0.02