## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15262 | New | Construction of different components of Lakhipara Tea Garden PWSS i.e. TW, Pump House, Water distribution Network, OHR , Rising Main, FHTC etc. in connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000492/2022-2023 | 824/JD | 30/03/2023 | 02/07/2026 | S.S. CONSTRUCTION | 297.96 | 225.12 | 75.55 | 70
2 | JALPAIGURI | Dhupguri | Northern Mechanical | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15262 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for LAKSHMIPARA TG PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000430/2023-2024 | 1369/NMD | 09/08/2023 | 01/10/2024 | GEETA CONSTRUCTION | 24.87 | 23.74 | 95.47 | 100
3 | JALPAIGURI | Dhupguri | Jalpaiguri Division | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15262 | New | Material Requisition To Resource Division |  |  | RTOR000025/2023-2024 | 169/JD | 28/04/2023 | 28/04/2023 | Resource Division | 12.25 | 0 | 0 | 0
4 | JALPAIGURI | Dhupguri | Jalpaiguri Division | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15262 | New | Material Requisition To Resource Division |  |  | RTOR000120/2023-2024 | 1834/JD | 15/12/2023 | 15/12/2023 | Resource Division | 7.44 | 0 | 0 | 0
5 | JALPAIGURI | Dhupguri | Jalpaiguri Division | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15262 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
6 | JALPAIGURI | Dhupguri | Northern Mechanical | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15262 | New | New Service Connection Charge for LAKSHMIPARA T.G., T/W No. II, under BAHARHAT CCC [APPLICATION NO. 4003254888 ; Reference ID : 403095711] |  |  | BILL/01725/2023-2024 | BP/23-24/248 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
7 | JALPAIGURI | Dhupguri | Northern Mechanical | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15262 | New | New Service Connection Charge for LAKSHMIPARA T.G., T/W No. I, under BAHARHAT CCC [APPLICATION NO. 4003254880 ; Reference ID : 403095717] |  |  | BILL/01723/2023-2024 | BP/23-24/246 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
8 | JALPAIGURI | Dhupguri | Northern Mechanical | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15262 | New | Infrastructure Cost for LAKSHMIPARA T.G., T/W No. I, under BAHARHAT CCC [APPLICATION NO. 100000091681 ; Reference ID : 860283231] |  |  | BILL/01724/2023-2024 | BP/23-24/247 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.26 | 0 | 0 | 0
9 | JALPAIGURI | Dhupguri | Northern Mechanical | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15262 | New | Infrastructure Cost for LAKSHMIPARA T.G., T/W No. II, under BAHARHAT CCC [APPLICATION NO. 100000091682 ; Reference ID : 860283232] |  |  | BILL/01726/2023-2024 | BP/23-24/249 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.71 | 0 | 0 | 0
10 | JALPAIGURI | Dhupguri | Northern Mechanical | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15262 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (BANARHAT Block ) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000987/2024-2025 | 11/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 57.53 | 0 | 0 | 0
11 | JALPAIGURI | Dhupguri | Northern Mechanical | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15262 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: BANARHAT, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/001041/2024-2025 | 29/NMD | 06/01/2025 | 05/02/2025 | DIAMOND ELECTRICAL WORKS | 12.26 | 0 | 0 | 0
12 | JALPAIGURI | Dhupguri | Jalpaiguri Division | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15262 | New | Continuation order for the work of hiring of 1 (one) number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver, in good condition under the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under AE(HQ). (Vehicle No. WB-71B-1991), (From 01.04.2025 to 30.04.2025) | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000789/2024-2025 | 110-HQ/JD | 28/03/2025 | 28/04/2025 | AJIJUL HAQUE | 0.15 | 0 | 0 | 0
13 | JALPAIGURI | Dhupguri | Northern Mechanical | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15262 | New | Installation of two tank chlorination system at different water supply scheme UNDER JJM under BANARHAT Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Driller-in-Charge |  | ORD/001136/2024-2025 | 52/DSD | 10/03/2025 | 25/03/2025 | D.K. & SONS | 1.39 | 0 | 0 | 0
14 | JALPAIGURI | Dhupguri | Northern Mechanical | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15262 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
15 | JALPAIGURI | Dhupguri | Jalpaiguri Division | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15262 | New | Material Requisition To Resource Division |  |  | RTOR000096/2024-2025 | 289/JD | 10/02/2025 | 10/02/2025 | Resource Division | 37.41 | 0 | 0 | 0
Total | [13 empty] | 1040.83 | 248.86 | 23.91