## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Rajganj | Jalpaiguri Division | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME | SM/15263 | New | Material Requisition To Resource Division |  |  | RTOR000186/2023-2024 | 2049/JD | 09/01/2024 | 09/01/2024 | Resource Division | 7.47 | 0 | 0 | 0
2 | JALPAIGURI | Rajganj | Jalpaiguri Division | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME | SM/15263 | New | Material Requisition To Resource Division |  |  | RTOR000005/2024-2025 | 53/JD | 09/04/2024 | 09/04/2024 | Resource Division | 13.2 | 0 | 0 | 0
3 | JALPAIGURI | Rajganj | Northern Mechanical | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME | SM/15263 | New | New Service Connection Charge for KHOLA CHAND FAPRI, TW NO-I, POWER HOUSE CCC APPLICATION NO. 4003352414 Consumer ID : 403172861 |  |  | BILL/00524/2024-2025 | BP/24-25/123 | 16/07/2024 | 16/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.99 | 0 | 0 | 0
4 | JALPAIGURI | Rajganj | Northern Mechanical | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME | SM/15263 | New | New Service Connection Charge for KHOLA CHAND FAPRI, TW NO-II, Powe House CCC APPLICATION NO. 4003352425 Reference ID : 403172863 |  |  | BILL/00435/2024-2025 | BP/24-25/87 | 18/06/2024 | 18/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 15.71 | 0 | 0 | 0
5 | JALPAIGURI | Rajganj | Jalpaiguri Division | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME | SM/15263 | New | Construction of different components of Kholachand Fapri PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. under Jal Jeevan Mission at Block - Rajganj under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000064/2023-2024 | 266/JD | 10/05/2023 | 06/11/2023 | M/S SARKAR ENTERPRISE | 262.01 | 0 | 0 | 35
6 | JALPAIGURI | Rajganj | Northern Mechanical | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME | SM/15263 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KHOLACHAND FAPRI PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000311/2023-2024 | 1276/NMD | 02/08/2023 | 01/04/2025 | P.K.ENGINEERING | 22.11 | 8.22 | 37.2 | 50
7 | JALPAIGURI | Rajganj | Northern Mechanical | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME | SM/15263 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (RAJGANJ Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000627/2024-2025 | 9/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 45.53 | 0 | 0 | 0
8 | JALPAIGURI | Rajganj | Jalpaiguri Division | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME | SM/15263 | New | Sub-Soil Investigation of proposed 200 cum capacity Over Head Reservoir with 20 mtr. staging height, below the depth greater than 10 mtr. to 30 mtr. from G. L. at the Head Works site of Kholachand Fapri Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000800/2024-2025 | 87-HQ/JD | 11/03/2025 | 31/03/2025 | APEX ENGINEERING | 0.98 | 0 | 0 | 0
9 | JALPAIGURI | Rajganj | Jalpaiguri Division | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME | SM/15263 | New | Material Requisition To Resource Division |  |  | RTOR000101/2024-2025 | 510/JD | 13/03/2025 | 13/03/2025 | Resource Division | 47.46 | 0 | 0 | 0
10 | JALPAIGURI | Rajganj | Jalpaiguri Division | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME | SM/15263 | New | Payment for NPV Demand note and cost compensatory Afforestation Area use 0.1125 ha forest in favour of West Bengal Public Health Engineering Directorate For water supply scheme under Jal Jeevan Mission (JJM) under Baikunthapur forest division - regarding proposal no -FP/WB/WATER/457969/2024 . |  |  | BILL/01090/2024-2025 | BP-2024-25-599 | 27/01/2025 | 27/01/2025 | DIVISIONAL FOREST OFFICER, BAIKUNTHAPUR DIVISION | 6.01 | 0 | 0 | 0
11 | JALPAIGURI | Rajganj | Jalpaiguri Division | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME | SM/15263 | New | Deposit amount for construction of boundary pillar regarding Ref- proposal no - FP/WB/WATER/471779/2024 |  |  | BILL/01239/2024-2025 | BP-2024-25-604 | 13/03/2025 | 13/03/2025 | DIVISIONAL FOREST OFFICER, BAIKUNTHAPUR DIVISION | 0.6 | 0 | 0 | 0
Total | [13 empty] | 430.08 | 8.22 | 1.91