## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Matiali | Jalpaiguri Division | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15264 | New | Sinking of 2 Nos Deep Rig Bored Tube Well by ODEX-195 method of drilling with 2 Nos Pump House(3.6m X 2.4m) and Boundary Wall including Pump House to distribution Line Connection for Rejuvenation of Chalsa Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000275/2023-2024 | 614/JD | 30/06/2023 | 30/07/2023 | S. N. POLYMERS PVT. LTD. | 40.47 | 13.79 | 34.07 | 35
2 | JALPAIGURI | Matiali | Jalpaiguri Division | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15264 | New | Retrofitting and Repairing work related to Laying Distribution System in Mangal Bar market area at Chalsa Rejuvenation Water Supply Scheme under Jalpaiguri Division, PHE DTE. |  | Junior Engineer | ORD/000829/2021-2022 | 1072/W/JSSD | 25/01/2022 | 14/02/2022 | DEEP CONSTRUCTION | 4.14 | 4.09 | 98.72 | 0
3 | JALPAIGURI | Matiali | Northern Mechanical | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15264 | New | Infrastructure Cost for CHALSA TEA GARDEN, T/W I, under METTALI CCC, [APPLICATION NO. 100000084427, Reference ID : 860276303] |  |  | BILL/00608/2023-2024 | BP/23-24/85 | 18/08/2023 | 18/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.14 | 0 | 0 | 0
4 | JALPAIGURI | Matiali | Northern Mechanical | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15264 | New | New Service Connection Charge for CHALSA TEA GARDEN, T/W I, under METTALI CCC, [APPLICATION NO. 4003197396, Reference ID : 403049082] |  |  | BILL/00607/2023-2024 | BP/23-24/85 | 18/08/2023 | 18/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
5 | JALPAIGURI | Matiali | Northern Mechanical | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15264 | New | New Service Connection Charge for CHALSA TEA GARDEN, T/W II, under METTALI CCC, [APPLICATION NO. 4003197399, Reference ID : 403049084] |  |  | BILL/00609/2023-2024 | BP/23-24/85 | 18/08/2023 | 18/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
6 | JALPAIGURI | Matiali | Northern Mechanical | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15264 | New | Infrastructure Cost for CHALSA TEA GARDEN, T/W II, under METTALI CCC, [APPLICATION NO. 100000084429, Reference ID : 860276310] |  |  | BILL/00610/2023-2024 | BP/23-24/85 | 18/08/2023 | 18/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6 | 0 | 0 | 0
7 | JALPAIGURI | Matiali | Jalpaiguri Division | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15264 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
8 | JALPAIGURI | Matiali | Jalpaiguri Division | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15264 | New | Material Requisition To Resource Division |  |  | RTOR000172/2023-2024 | 2034/JD | 09/01/2024 | 09/01/2024 | Resource Division | 6.65 | 0 | 0 | 0
9 | JALPAIGURI | Matiali | Jalpaiguri Division | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15264 | New | Construction of different components of Chalsa Tea Graden PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, BW, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block Matiali under Jalpaiguri Division. | Assistant Engineer | Junior Engineer | ORD/000006/2023-2024 | 24/JD | 10/04/2023 | 01/10/2025 | PRASENJIT BASAK | 195.5 | 118.79 | 60.76 | 90
10 | JALPAIGURI | Matiali | Northern Mechanical | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15264 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (MATIALI Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000993/2024-2025 | 13/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 36.03 | 0 | 0 | 0
11 | JALPAIGURI | Matiali | Northern Mechanical | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15264 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
12 | JALPAIGURI | Matiali | Jalpaiguri Division | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15264 | New | Balance work of Distribution System and Functional Household Tap Connection (FHTC) of Chalsa Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000184/2025-2026 | 2157/JD | 29/10/2025 | 28/11/2025 | PRASENJIT BASAK | 14.85 | 0 | 0 | 0
Total | [13 empty] | 888.37 | 136.67 | 15.38