## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15296 | New | Construction of different components of Nipuchhapur PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000049/2023-2024 | 242/JD | 08/05/2023 | 06/08/2025 | M/S SURAJIT DEY AND CO. | 335.86 | 179.3 | 53.39 | 60
2 | JALPAIGURI | Mal | Northern Mechanical | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15296 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for NIPUCHHAPUR PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000461/2023-2024 | 1437/NMD | 10/08/2023 | 01/02/2025 | S.P. ENTERPRISE | 27.2 | 18.04 | 66.33 | 80
3 | JALPAIGURI | Mal | Jalpaiguri Division | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15296 | New | Material Requisition To Resource Division |  |  | RTOR000071/2023-2024 | 1076/JD | 24/08/2023 | 24/08/2023 | Resource Division | 32.73 | 0 | 0 | 0
4 | JALPAIGURI | Mal | Jalpaiguri Division | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15296 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
5 | JALPAIGURI | Mal | Jalpaiguri Division | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15296 | New | Balance work of Distribution System and Functional Household Tap Connection (FHTC) including Different Components of Nipucchapur TG PWSS i.e. TW, Pump House, Boundary Wall, Rising main etc. in connection with Jal Jeevan Mission at Block-Mal under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000420/2024-2025 | 2266/JD | 04/12/2024 | 01/04/2026 | MALAY BHOWMIK | 49.56 | 0 | 0 | 0
6 | JALPAIGURI | Mal | Jalpaiguri Division | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15296 | New | Material Requisition To Resource Division |  |  | RTOR000194/2023-2024 | 2039/JD | 09/01/2024 | 09/01/2024 | Resource Division | 11.29 | 0 | 0 | 0
7 | JALPAIGURI | Mal | Northern Mechanical | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15296 | New | New Service Connection Charge for NIPUCHHAPUR TG, TW NO-II, MAL CCC APPLICATION NO. 4003352328 Reference ID : 403172832 |  |  | BILL/00177/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
8 | JALPAIGURI | Mal | Northern Mechanical | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15296 | New | Infrastructure development cost for new service connection at NIPUCHHAPUR TG, TW NO-I, MAL CCC APPLICATION NO. 100000104478 Reference ID : 860297008 |  |  | BILL/00176/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.67 | 0 | 0 | 0
9 | JALPAIGURI | Mal | Northern Mechanical | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15296 | New | New Service Connection Charge for NIPUCHHAPUR TG, TW NO-I, MAL CCC APPLICATION NO. 4003352325 Reference ID : 403172833 |  |  | BILL/00175/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
10 | JALPAIGURI | Mal | Northern Mechanical | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15296 | New | Infrastructure development cost for new service connection at NIPUCHHAPUR TG, TW NO-II, MAL CCC APPLICATION NO. 100000104479 Reference ID : 860297009 |  |  | BILL/00178/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.89 | 0 | 0 | 0
11 | JALPAIGURI | Mal | Jalpaiguri Division | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15296 | New | Construction approach with paver block inside the premises and land development at HW site & 2nd TW Site of Nipucchapur TG Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000176/2025-2026 | 175/JSSD | 25/07/2025 | 24/08/2025 | TEESTA CO OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCITY LIMITED. | 7.59 | 0 | 0 | 0
12 | JALPAIGURI | Mal | Northern Mechanical | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15296 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
Total | [13 empty] | 644.13 | 197.34 | 30.64